## Modules
ModuleCode | QuoteRef | ModuleName | Description | InstructionText | EstimatedHours | StockOnHand | Status | CreatedOn | UpdatedOn
ASM-001 | Q-001 | Buck Weld 2 inch | Buck weld unit for 2 inch standpipe; 30 minutes each. | Build Buck Weld 2 inch | 0.5 | 3 | Released | 2025-12-04 00:00:00 | 2026-03-13 00:00:00
ASM-002 | Q-002 | Steel Bend 2 inch | Steel bend assembly for 2 inch standpipe. | Build Steel Bend 2 inch | 0.75 | 1 | Released | 2025-12-09 00:00:00 | 2026-03-15 00:00:00
ASM-003 | Q-003 | Buck Weld 4 inch | Buck weld unit for 4 inch standpipe; 30 minutes each. | Build Buck Weld 4 inch | 0.5 | 5 | Released | 2026-02-22 00:00:00 | 2026-03-18 00:00:00
ASM-004 | Q-004 | Steel Bend 4 inch | Steel bend assembly for 4 inch standpipe. | Build Steel Bend 4 inch | 0.75 | 6 | Released | 2026-01-05 00:00:00 | 2026-03-14 00:00:00
ASM-005 | Q-005 | Buck Weld 6 inch | Buck weld unit for 6 inch standpipe; 30 minutes each. | Build Buck Weld 6 inch | 0.5 | 2 | Released | 2026-01-23 00:00:00 | 2026-03-17 00:00:00
ASM-006 | Q-006 | Steel Bend 6 inch | Steel bend assembly for 6 inch standpipe. | Build Steel Bend 6 inch | 0.75 | 5 | Released | 2025-12-28 00:00:00 | 2026-03-15 00:00:00
ASM-007 | Q-007 | Buck Weld 8 inch | Buck weld unit for 8 inch standpipe; 30 minutes each. | Build Buck Weld 8 inch | 0.5 | 7 | Released | 2025-12-30 00:00:00 | 2026-03-16 00:00:00
ASM-008 | Q-008 | Steel Bend 8 inch | Steel bend assembly for 8 inch standpipe. | Build Steel Bend 8 inch | 0.75 | 9 | Released | 2026-01-23 00:00:00 | 2026-03-13 00:00:00
ASM-009 | Q-009 | Buck Weld 10 inch | Buck weld unit for 10 inch standpipe; 30 minutes each. | Build Buck Weld 10 inch | 0.5 | 2 | Released | 2026-01-31 00:00:00 | 2026-03-15 00:00:00
ASM-010 | Q-010 | Steel Bend 10 inch | Steel bend assembly for 10 inch standpipe. | Build Steel Bend 10 inch | 0.75 | 6 | Released | 2026-02-19 00:00:00 | 2026-03-11 00:00:00
ASM-011 | Q-011 | Telemetry Unit 12V | Telemetry Unit 12V assembly template | Build Telemetry Unit 12V | 2.5 | 0 | Released | 2026-01-13 00:00:00 | 2026-03-16 00:00:00
ASM-012 | Q-012 | Frame Steel Work | Frame Steel Work assembly template | Build Frame Steel Work | 3 | 1 | Released | 2026-01-06 00:00:00 | 2026-03-10 00:00:00
ASM-013 | Q-013 | Frame to Solar Panel Assembly | Frame to Solar Panel Assembly assembly template | Build Frame to Solar Panel Assembly | 1.25 | 3 | Released | 2026-01-12 00:00:00 | 2026-03-18 00:00:00
ASM-014 | Q-014 | Build Control Panel | Build Control Panel assembly template | Build Build Control Panel | 4 | 1 | Released | 2026-01-15 00:00:00 | 2026-03-18 00:00:00
ASM-015 | Q-015 | Final Integration | Final Integration assembly template | Build Final Integration | 2 | 3 | Released | 2026-02-25 00:00:00 | 2026-03-15 00:00:00
ASM-016 | Q-016 | AC Power Distribution | AC Power Distribution assembly template | Build AC Power Distribution | 2 | 4 | Released | 2025-11-22 00:00:00 | 2026-03-16 00:00:00
ASM-017 | Q-017 | DC Battery Rack | DC Battery Rack assembly template | Build DC Battery Rack | 2 | 0 | Released | 2026-01-24 00:00:00 | 2026-03-11 00:00:00
ASM-018 | Q-018 | Hybrid Changeover Assembly | Hybrid Changeover Assembly assembly template | Build Hybrid Changeover Assembly | 2.5 | 10 | Released | 2025-12-07 00:00:00 | 2026-03-15 00:00:00
ASM-019 | Q-019 | Pontoon Float Pack | Pontoon Float Pack assembly template | Build Pontoon Float Pack | 3 | 5 | Released | 2026-01-06 00:00:00 | 2026-03-17 00:00:00
ASM-020 | Q-020 | Pontoon Frame Build | Pontoon Frame Build assembly template | Build Pontoon Frame Build | 3.5 | 1 | Released | 2025-11-18 00:00:00 | 2026-03-17 00:00:00
ASM-021 | Q-021 | Winch Mast Assembly | Winch Mast Assembly assembly template | Build Winch Mast Assembly | 2.5 | 9 | Released | 2025-11-21 00:00:00 | 2026-03-10 00:00:00
ASM-022 | Q-022 | Pump Guide Rail | Pump Guide Rail assembly template | Build Pump Guide Rail | 2 | 7 | Released | 2026-01-11 00:00:00 | 2026-03-10 00:00:00
ASM-023 | Q-023 | Dust Fan Skid | Dust Fan Skid assembly template | Build Dust Fan Skid | 3 | 8 | Released | 2026-01-01 00:00:00 | 2026-03-18 00:00:00
ASM-024 | Q-024 | Spray Manifold | Spray Manifold assembly template | Build Spray Manifold | 2 | 9 | Released | 2026-02-10 00:00:00 | 2026-03-13 00:00:00
ASM-025 | Q-025 | Telemetry Retrofit Bracket | Telemetry Retrofit Bracket assembly template | Build Telemetry Retrofit Bracket | 1.2 | 10 | Released | 2026-02-13 00:00:00 | 2026-03-17 00:00:00
ASM-026 | Q-026 | Solar Controller Board | Solar Controller Board assembly template | Build Solar Controller Board | 2 | 2 | Released | 2026-01-19 00:00:00 | 2026-03-15 00:00:00
ASM-027 | Q-027 | Kiosk Frame Build | Kiosk Frame Build assembly template | Build Kiosk Frame Build | 2.8 | 10 | Released | 2025-12-16 00:00:00 | 2026-03-17 00:00:00
ASM-028 | Q-028 | Remote Pump Skid | Remote Pump Skid assembly template | Build Remote Pump Skid | 3.2 | 4 | Released | 2025-12-13 00:00:00 | 2026-03-13 00:00:00
ASM-029 | Q-029 | Poly Access Riser | Poly Access Riser assembly template | Build Poly Access Riser | 1.5 | 1 | Released | 2025-12-22 00:00:00 | 2026-03-15 00:00:00
ASM-030 | Q-030 | Tank Sensor Loom | Tank Sensor Loom assembly template | Build Tank Sensor Loom | 1.75 | 8 | Released | 2025-11-29 00:00:00 | 2026-03-12 00:00:00
ASM-031 | Q-031 | Valve Meter Panel Build | Valve Meter Panel Build assembly template | Build Valve Meter Panel Build | 2.8 | 9 | Released | 2025-12-05 00:00:00 | 2026-03-15 00:00:00
ASM-032 | Q-032 | Pump Control Panel | Pump Control Panel assembly template | Build Pump Control Panel | 3 | 5 | Released | 2025-12-25 00:00:00 | 2026-03-13 00:00:00
ASM-033 | Q-033 | Solar Mount Assembly | Solar Mount Assembly assembly template | Build Solar Mount Assembly | 2 | 8 | Released | 2026-01-12 00:00:00 | 2026-03-15 00:00:00
ASM-034 | Q-034 | Winch Control Assembly | Winch Control Assembly assembly template | Build Winch Control Assembly | 1.8 | 8 | Released | 2026-01-14 00:00:00 | 2026-03-11 00:00:00
ASM-035 | Q-035 | Dust Suppression Control Panel | Dust Suppression Control Panel assembly template | Build Dust Suppression Control Panel | 2.6 | 2 | Released | 2026-01-21 00:00:00 | 2026-03-10 00:00:00

## Tasks
TaskID | OwnerType | OwnerCode | TaskName | Department | EstimatedHours | ParentTaskID | DependencyTaskID | Stage | Status | Notes | CreatedOn | UpdatedOn
T::ASM-001::01 | MODULE | ASM-001 | Buck weld setup | Fabrication | 0.2 |  |  | Assembly | Not Started | Default owner: Alex | 2025-11-18 00:00:00 | 2026-03-16 00:00:00
T::ASM-001::02 | MODULE | ASM-001 | Buck weld fit-off | Operations/Assembly | 0.3 |  | T::ASM-001::01 | Assembly | Not Started | Default owner: Raj | 2025-12-28 00:00:00 | 2026-03-16 00:00:00
T::ASM-002::01 | MODULE | ASM-002 | Bend prep | Fabrication | 0.35 |  |  | Assembly | Not Started | Default owner: Alex | 2025-12-16 00:00:00 | 2026-03-12 00:00:00
T::ASM-002::02 | MODULE | ASM-002 | Bend finish | Operations/Assembly | 0.4 |  | T::ASM-002::01 | Assembly | Not Started | Default owner: Raj | 2025-12-02 00:00:00 | 2026-03-14 00:00:00
T::ASM-003::01 | MODULE | ASM-003 | Buck weld setup | Fabrication | 0.2 |  |  | Assembly | Not Started | Default owner: Alex | 2026-02-12 00:00:00 | 2026-03-17 00:00:00
T::ASM-003::02 | MODULE | ASM-003 | Buck weld fit-off | Operations/Assembly | 0.3 |  | T::ASM-003::01 | Assembly | Not Started | Default owner: Raj | 2026-02-08 00:00:00 | 2026-03-17 00:00:00
T::ASM-004::01 | MODULE | ASM-004 | Bend prep | Fabrication | 0.35 |  |  | Assembly | Not Started | Default owner: Alex | 2026-01-17 00:00:00 | 2026-03-13 00:00:00
T::ASM-004::02 | MODULE | ASM-004 | Bend finish | Operations/Assembly | 0.4 |  | T::ASM-004::01 | Assembly | Not Started | Default owner: Raj | 2025-11-19 00:00:00 | 2026-03-13 00:00:00
T::ASM-005::01 | MODULE | ASM-005 | Buck weld setup | Fabrication | 0.2 |  |  | Assembly | Not Started | Default owner: Alex | 2026-02-17 00:00:00 | 2026-03-13 00:00:00
T::ASM-005::02 | MODULE | ASM-005 | Buck weld fit-off | Operations/Assembly | 0.3 |  | T::ASM-005::01 | Assembly | Not Started | Default owner: Raj | 2026-01-07 00:00:00 | 2026-03-16 00:00:00
T::ASM-006::01 | MODULE | ASM-006 | Bend prep | Fabrication | 0.35 |  |  | Assembly | Not Started | Default owner: Alex | 2025-12-01 00:00:00 | 2026-03-11 00:00:00
T::ASM-006::02 | MODULE | ASM-006 | Bend finish | Operations/Assembly | 0.4 |  | T::ASM-006::01 | Assembly | Not Started | Default owner: Raj | 2026-01-20 00:00:00 | 2026-03-16 00:00:00
T::ASM-007::01 | MODULE | ASM-007 | Buck weld setup | Fabrication | 0.2 |  |  | Assembly | Not Started | Default owner: Alex | 2026-01-08 00:00:00 | 2026-03-13 00:00:00
T::ASM-007::02 | MODULE | ASM-007 | Buck weld fit-off | Operations/Assembly | 0.3 |  | T::ASM-007::01 | Assembly | Not Started | Default owner: Raj | 2026-02-10 00:00:00 | 2026-03-11 00:00:00
T::ASM-008::01 | MODULE | ASM-008 | Bend prep | Fabrication | 0.35 |  |  | Assembly | Not Started | Default owner: Alex | 2026-01-01 00:00:00 | 2026-03-17 00:00:00
T::ASM-008::02 | MODULE | ASM-008 | Bend finish | Operations/Assembly | 0.4 |  | T::ASM-008::01 | Assembly | Not Started | Default owner: Raj | 2026-01-07 00:00:00 | 2026-03-10 00:00:00
T::ASM-009::01 | MODULE | ASM-009 | Buck weld setup | Fabrication | 0.2 |  |  | Assembly | Not Started | Default owner: Alex | 2026-02-16 00:00:00 | 2026-03-10 00:00:00
T::ASM-009::02 | MODULE | ASM-009 | Buck weld fit-off | Operations/Assembly | 0.3 |  | T::ASM-009::01 | Assembly | Not Started | Default owner: Raj | 2026-02-01 00:00:00 | 2026-03-11 00:00:00
T::ASM-010::01 | MODULE | ASM-010 | Bend prep | Fabrication | 0.35 |  |  | Assembly | Not Started | Default owner: Alex | 2025-11-22 00:00:00 | 2026-03-13 00:00:00
T::ASM-010::02 | MODULE | ASM-010 | Bend finish | Operations/Assembly | 0.4 |  | T::ASM-010::01 | Assembly | Not Started | Default owner: Raj | 2026-01-05 00:00:00 | 2026-03-10 00:00:00
T::ASM-011::01 | MODULE | ASM-011 | Telemetry layout | Electrical/Automation | 0.6 |  |  | Design | Not Started | Default owner: Sachin | 2026-01-08 00:00:00 | 2026-03-18 00:00:00
T::ASM-011::02 | MODULE | ASM-011 | Battery and solar fitout | Electrical/Automation | 1 |  | T::ASM-011::01 | Assembly | Not Started | Default owner: Sachin | 2025-11-21 00:00:00 | 2026-03-14 00:00:00
T::ASM-011::03 | MODULE | ASM-011 | Telemetry commissioning | Software | 0.9 |  | T::ASM-011::02 | Testing | Not Started | Default owner: Aayush | 2025-12-18 00:00:00 | 2026-03-15 00:00:00
T::ASM-012::01 | MODULE | ASM-012 | Frame drawing review | GA Drawing/Mechanical | 0.5 |  |  | Design | Not Started | Default owner: Ryan | 2025-12-11 00:00:00 | 2026-03-15 00:00:00
T::ASM-012::02 | MODULE | ASM-012 | Frame fabrication | Fabrication | 1.8 |  | T::ASM-012::01 | Assembly | Not Started | Default owner: Alex | 2026-02-12 00:00:00 | 2026-03-10 00:00:00
T::ASM-012::03 | MODULE | ASM-012 | Frame finish | Operations/Assembly | 0.7 |  | T::ASM-012::02 | Assembly | Not Started | Default owner: Raj | 2025-12-02 00:00:00 | 2026-03-17 00:00:00
T::ASM-013::01 | MODULE | ASM-013 | Fit frame to panel | Fabrication | 0.5 |  |  | Assembly | Not Started | Default owner: Alex | 2026-02-14 00:00:00 | 2026-03-10 00:00:00
T::ASM-013::02 | MODULE | ASM-013 | Panel mounting | Operations/Assembly | 0.75 |  | T::ASM-013::01 | Assembly | Not Started | Default owner: Raj | 2025-12-28 00:00:00 | 2026-03-17 00:00:00
T::ASM-014::01 | MODULE | ASM-014 | Panel design | Electrical/Automation | 1 |  |  | Design | Not Started | Default owner: Sachin | 2025-11-27 00:00:00 | 2026-03-16 00:00:00
T::ASM-014::02 | MODULE | ASM-014 | Panel build | Electrical/Automation | 2 |  | T::ASM-014::01 | Assembly | Not Started | Default owner: Sachin | 2026-02-08 00:00:00 | 2026-03-10 00:00:00
T::ASM-014::03 | MODULE | ASM-014 | Panel test | Software | 1 |  | T::ASM-014::02 | Testing | Not Started | Default owner: Aayush | 2025-12-27 00:00:00 | 2026-03-11 00:00:00
T::ASM-015::01 | MODULE | ASM-015 | Mechanical integration | Operations/Assembly | 1 |  |  | Assembly | Not Started | Default owner: Raj | 2026-02-19 00:00:00 | 2026-03-18 00:00:00
T::ASM-015::02 | MODULE | ASM-015 | I/O integration | Electrical/Automation | 0.5 |  | T::ASM-015::01 | Assembly | Not Started | Default owner: Sachin | 2025-12-28 00:00:00 | 2026-03-17 00:00:00
T::ASM-015::03 | MODULE | ASM-015 | Final commissioning | Software | 0.5 |  | T::ASM-015::02 | Testing | Not Started | Default owner: Aayush | 2026-02-03 00:00:00 | 2026-03-10 00:00:00
T::ASM-016::01 | MODULE | ASM-016 | AC design | Electrical/Automation | 0.6 |  |  | Design | Not Started | Default owner: Sachin | 2026-01-07 00:00:00 | 2026-03-16 00:00:00
T::ASM-016::02 | MODULE | ASM-016 | AC panel build | Electrical/Automation | 1 |  | T::ASM-016::01 | Assembly | Not Started | Default owner: Sachin | 2026-01-12 00:00:00 | 2026-03-13 00:00:00
T::ASM-016::03 | MODULE | ASM-016 | AC verification | Operations/Assembly | 0.4 |  | T::ASM-016::02 | Testing | Not Started | Default owner: Raj | 2026-01-21 00:00:00 | 2026-03-10 00:00:00
T::ASM-017::01 | MODULE | ASM-017 | Rack fabrication | Fabrication | 0.8 |  |  | Assembly | Not Started | Default owner: Alex | 2025-12-15 00:00:00 | 2026-03-11 00:00:00
T::ASM-017::02 | MODULE | ASM-017 | Battery fitout | Electrical/Automation | 0.8 |  | T::ASM-017::01 | Assembly | Not Started | Default owner: Sachin | 2025-11-18 00:00:00 | 2026-03-13 00:00:00
T::ASM-017::03 | MODULE | ASM-017 | Safety check | Operations/Assembly | 0.4 |  | T::ASM-017::02 | Testing | Not Started | Default owner: Raj | 2026-01-17 00:00:00 | 2026-03-17 00:00:00
T::ASM-018::01 | MODULE | ASM-018 | Changeover wiring | Electrical/Automation | 1.2 |  |  | Assembly | Not Started | Default owner: Sachin | 2025-12-07 00:00:00 | 2026-03-13 00:00:00
T::ASM-018::02 | MODULE | ASM-018 | Switch testing | Software | 0.5 |  | T::ASM-018::01 | Testing | Not Started | Default owner: Aayush | 2026-02-25 00:00:00 | 2026-03-15 00:00:00
T::ASM-018::03 | MODULE | ASM-018 | Final QA | Operations/Assembly | 0.8 |  | T::ASM-018::02 | Testing | Not Started | Default owner: Raj | 2025-12-28 00:00:00 | 2026-03-14 00:00:00
T::ASM-019::01 | MODULE | ASM-019 | Float layout | GA Drawing/Mechanical | 0.5 |  |  | Design | Not Started | Default owner: Ryan | 2025-11-19 00:00:00 | 2026-03-10 00:00:00
T::ASM-019::02 | MODULE | ASM-019 | Pontoon assembly | Fabrication | 1.5 |  | T::ASM-019::01 | Assembly | Not Started | Default owner: Alex | 2025-12-16 00:00:00 | 2026-03-13 00:00:00
T::ASM-019::03 | MODULE | ASM-019 | Pontoon final fit | Operations/Assembly | 1 |  | T::ASM-019::02 | Assembly | Not Started | Default owner: Raj | 2025-12-04 00:00:00 | 2026-03-12 00:00:00
T::ASM-020::01 | MODULE | ASM-020 | Frame cut list | GA Drawing/Mechanical | 0.5 |  |  | Design | Not Started | Default owner: Ryan | 2026-01-31 00:00:00 | 2026-03-14 00:00:00
T::ASM-020::02 | MODULE | ASM-020 | Frame fabrication | Fabrication | 2 |  | T::ASM-020::01 | Assembly | Not Started | Default owner: Alex | 2026-02-11 00:00:00 | 2026-03-17 00:00:00
T::ASM-020::03 | MODULE | ASM-020 | Frame finish | Operations/Assembly | 1 |  | T::ASM-020::02 | Assembly | Not Started | Default owner: Raj | 2026-01-05 00:00:00 | 2026-03-12 00:00:00
T::ASM-021::01 | MODULE | ASM-021 | Mast fabrication | Fabrication | 1 |  |  | Assembly | Not Started | Default owner: Alex | 2025-11-19 00:00:00 | 2026-03-16 00:00:00
T::ASM-021::02 | MODULE | ASM-021 | Winch install | Operations/Assembly | 1 |  | T::ASM-021::01 | Assembly | Not Started | Default owner: Raj | 2026-02-15 00:00:00 | 2026-03-12 00:00:00
T::ASM-021::03 | MODULE | ASM-021 | Movement test | Operations/Assembly | 0.5 |  | T::ASM-021::02 | Testing | Not Started | Default owner: Raj | 2025-12-14 00:00:00 | 2026-03-11 00:00:00
T::ASM-022::01 | MODULE | ASM-022 | Rail fabrication | Fabrication | 1 |  |  | Assembly | Not Started | Default owner: Alex | 2025-11-25 00:00:00 | 2026-03-11 00:00:00
T::ASM-022::02 | MODULE | ASM-022 | Rail install | Operations/Assembly | 1 |  | T::ASM-022::01 | Assembly | Not Started | Default owner: Raj | 2025-12-30 00:00:00 | 2026-03-15 00:00:00
T::ASM-023::01 | MODULE | ASM-023 | Skid fabrication | Fabrication | 1.2 |  |  | Assembly | Not Started | Default owner: Alex | 2026-01-04 00:00:00 | 2026-03-11 00:00:00
T::ASM-023::02 | MODULE | ASM-023 | Motor install | Electrical/Automation | 1 |  | T::ASM-023::01 | Assembly | Not Started | Default owner: Sachin | 2025-12-30 00:00:00 | 2026-03-13 00:00:00
T::ASM-023::03 | MODULE | ASM-023 | Fan test | Operations/Assembly | 0.8 |  | T::ASM-023::02 | Testing | Not Started | Default owner: Raj | 2025-12-28 00:00:00 | 2026-03-10 00:00:00
T::ASM-024::01 | MODULE | ASM-024 | Manifold fabrication | Fabrication | 0.8 |  |  | Assembly | Not Started | Default owner: Alex | 2025-11-20 00:00:00 | 2026-03-11 00:00:00
T::ASM-024::02 | MODULE | ASM-024 | Nozzle fitout | Operations/Assembly | 0.7 |  | T::ASM-024::01 | Assembly | Not Started | Default owner: Raj | 2025-12-10 00:00:00 | 2026-03-12 00:00:00
T::ASM-024::03 | MODULE | ASM-024 | Flow test | Operations/Assembly | 0.5 |  | T::ASM-024::02 | Testing | Not Started | Default owner: Raj | 2026-02-22 00:00:00 | 2026-03-17 00:00:00
T::ASM-025::01 | MODULE | ASM-025 | Bracket fabrication | Fabrication | 0.6 |  |  | Assembly | Not Started | Default owner: Alex | 2026-01-26 00:00:00 | 2026-03-18 00:00:00
T::ASM-025::02 | MODULE | ASM-025 | Retrofit fitment | Operations/Assembly | 0.6 |  | T::ASM-025::01 | Assembly | Not Started | Default owner: Raj | 2026-01-24 00:00:00 | 2026-03-17 00:00:00
T::ASM-026::01 | MODULE | ASM-026 | Control board wiring | Electrical/Automation | 1.2 |  |  | Assembly | Not Started | Default owner: Sachin | 2025-12-03 00:00:00 | 2026-03-13 00:00:00
T::ASM-026::02 | MODULE | ASM-026 | Control board test | Software | 0.8 |  | T::ASM-026::01 | Testing | Not Started | Default owner: Aayush | 2025-12-24 00:00:00 | 2026-03-16 00:00:00
T::ASM-027::01 | MODULE | ASM-027 | Kiosk design | GA Drawing/Mechanical | 0.6 |  |  | Design | Not Started | Default owner: Ryan | 2025-12-04 00:00:00 | 2026-03-10 00:00:00
T::ASM-027::02 | MODULE | ASM-027 | Kiosk fabrication | Fabrication | 1.5 |  | T::ASM-027::01 | Assembly | Not Started | Default owner: Alex | 2026-01-21 00:00:00 | 2026-03-11 00:00:00
T::ASM-027::03 | MODULE | ASM-027 | Kiosk fitout | Operations/Assembly | 0.7 |  | T::ASM-027::02 | Assembly | Not Started | Default owner: Raj | 2026-01-27 00:00:00 | 2026-03-11 00:00:00
T::ASM-028::01 | MODULE | ASM-028 | Skid fabrication | Fabrication | 1.4 |  |  | Assembly | Not Started | Default owner: Alex | 2026-02-11 00:00:00 | 2026-03-11 00:00:00
T::ASM-028::02 | MODULE | ASM-028 | Pump mounting | Operations/Assembly | 1 |  | T::ASM-028::01 | Assembly | Not Started | Default owner: Raj | 2026-02-13 00:00:00 | 2026-03-18 00:00:00
T::ASM-028::03 | MODULE | ASM-028 | Pump test | Electrical/Automation | 0.8 |  | T::ASM-028::02 | Testing | Not Started | Default owner: Sachin | 2025-12-17 00:00:00 | 2026-03-10 00:00:00
T::ASM-029::01 | MODULE | ASM-029 | Riser prep | Fabrication | 0.5 |  |  | Assembly | Not Started | Default owner: Alex | 2026-01-02 00:00:00 | 2026-03-18 00:00:00
T::ASM-029::02 | MODULE | ASM-029 | Riser build | Operations/Assembly | 0.7 |  | T::ASM-029::01 | Assembly | Not Started | Default owner: Raj | 2025-12-21 00:00:00 | 2026-03-12 00:00:00
T::ASM-029::03 | MODULE | ASM-029 | Access check | Operations/Assembly | 0.3 |  | T::ASM-029::02 | Testing | Not Started | Default owner: Raj | 2026-01-26 00:00:00 | 2026-03-16 00:00:00
T::ASM-030::01 | MODULE | ASM-030 | Sensor wiring | Electrical/Automation | 0.8 |  |  | Assembly | Not Started | Default owner: Sachin | 2025-12-22 00:00:00 | 2026-03-14 00:00:00
T::ASM-030::02 | MODULE | ASM-030 | Gateway setup | Software | 0.5 |  | T::ASM-030::01 | Testing | Not Started | Default owner: Aayush | 2025-12-05 00:00:00 | 2026-03-16 00:00:00
T::ASM-030::03 | MODULE | ASM-030 | Final loom check | Operations/Assembly | 0.45 |  | T::ASM-030::02 | Testing | Not Started | Default owner: Raj | 2026-02-10 00:00:00 | 2026-03-12 00:00:00
T::ASM-031::01 | MODULE | ASM-031 | Panel layout | Electrical/Automation | 0.8 |  |  | Design | Not Started | Default owner: Sachin | 2026-02-02 00:00:00 | 2026-03-12 00:00:00
T::ASM-031::02 | MODULE | ASM-031 | Panel build | Electrical/Automation | 1.4 |  | T::ASM-031::01 | Assembly | Not Started | Default owner: Sachin | 2025-11-18 00:00:00 | 2026-03-14 00:00:00
T::ASM-031::03 | MODULE | ASM-031 | Panel FAT | Operations/Assembly | 0.6 |  | T::ASM-031::02 | Testing | Not Started | Default owner: Raj | 2026-01-29 00:00:00 | 2026-03-15 00:00:00
T::ASM-032::01 | MODULE | ASM-032 | Control panel layout | Electrical/Automation | 1 |  |  | Design | Not Started | Default owner: Sachin | 2026-02-02 00:00:00 | 2026-03-15 00:00:00
T::ASM-032::02 | MODULE | ASM-032 | Control panel build | Electrical/Automation | 1.4 |  | T::ASM-032::01 | Assembly | Not Started | Default owner: Sachin | 2026-01-07 00:00:00 | 2026-03-12 00:00:00
T::ASM-032::03 | MODULE | ASM-032 | PLC commissioning | Software | 0.6 |  | T::ASM-032::02 | Testing | Not Started | Default owner: Aayush | 2025-12-08 00:00:00 | 2026-03-10 00:00:00
T::ASM-033::01 | MODULE | ASM-033 | Mount fabrication | Fabrication | 0.8 |  |  | Assembly | Not Started | Default owner: Alex | 2025-11-20 00:00:00 | 2026-03-13 00:00:00
T::ASM-033::02 | MODULE | ASM-033 | Panel mount | Operations/Assembly | 0.8 |  | T::ASM-033::01 | Assembly | Not Started | Default owner: Raj | 2026-02-12 00:00:00 | 2026-03-16 00:00:00
T::ASM-033::03 | MODULE | ASM-033 | Alignment check | Operations/Assembly | 0.4 |  | T::ASM-033::02 | Testing | Not Started | Default owner: Raj | 2026-01-29 00:00:00 | 2026-03-12 00:00:00
T::ASM-034::01 | MODULE | ASM-034 | Winch control wiring | Electrical/Automation | 0.9 |  |  | Assembly | Not Started | Default owner: Sachin | 2026-01-29 00:00:00 | 2026-03-11 00:00:00
T::ASM-034::02 | MODULE | ASM-034 | Winch control test | Software | 0.4 |  | T::ASM-034::01 | Testing | Not Started | Default owner: Aayush | 2026-02-22 00:00:00 | 2026-03-11 00:00:00
T::ASM-034::03 | MODULE | ASM-034 | Final fit | Operations/Assembly | 0.5 |  | T::ASM-034::02 | Assembly | Not Started | Default owner: Raj | 2025-12-16 00:00:00 | 2026-03-11 00:00:00
T::ASM-035::01 | MODULE | ASM-035 | Control panel wiring | Electrical/Automation | 1.1 |  |  | Assembly | Not Started | Default owner: Sachin | 2026-01-14 00:00:00 | 2026-03-11 00:00:00
T::ASM-035::02 | MODULE | ASM-035 | Logic setup | Software | 0.7 |  | T::ASM-035::01 | Testing | Not Started | Default owner: Aayush | 2025-12-10 00:00:00 | 2026-03-16 00:00:00
T::ASM-035::03 | MODULE | ASM-035 | Final QA | Operations/Assembly | 0.8 |  | T::ASM-035::02 | Testing | Not Started | Default owner: Raj | 2025-12-28 00:00:00 | 2026-03-17 00:00:00
T::ASM-035::VERIFY_THE_WIRING::104825828388 | MODULE | ASM-035 | Verify the wiring | Software | 1.1 | T::ASM-035::01 |  | Assembly | Not Started | Default owner: Sachin | 2026-03-18 10:48:25 | 2026-03-18 10:48:25

## Components
ComponentID | OwnerType | OwnerCode | ComponentName | Qty | SOHQty | PreferredSupplier | LeadTimeDays | UnitPrice | PartNumber | Notes | CreatedOn | UpdatedOn
C::ASM-001::PRT-0004 | MODULE | ASM-001 | Buck Weld Insert 2 inch | 1 | 38 | Festo | 5 | Assembly BOM item | 2026-02-12 00:00:00 | 2026-03-18 00:00:00
C::ASM-001::PRT-0027 | MODULE | ASM-001 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2025-11-25 00:00:00 | 2026-03-12 00:00:00
C::ASM-002::PRT-0005 | MODULE | ASM-002 | Steel Bend Blank 2 inch | 1 | 30 | Blackwoods | 21 | Assembly BOM item | 2026-02-15 00:00:00 | 2026-03-16 00:00:00
C::ASM-002::PRT-0027 | MODULE | ASM-002 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2026-01-08 00:00:00 | 2026-03-12 00:00:00
C::ASM-003::PRT-0009 | MODULE | ASM-003 | Buck Weld Insert 4 inch | 1 | 35 | NHP | 14 | Assembly BOM item | 2026-01-27 00:00:00 | 2026-03-10 00:00:00
C::ASM-003::PRT-0027 | MODULE | ASM-003 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2025-12-26 00:00:00 | 2026-03-10 00:00:00
C::ASM-004::PRT-0010 | MODULE | ASM-004 | Steel Bend Blank 4 inch | 1 | 9 | Festo | 14 | Assembly BOM item | 2025-11-30 00:00:00 | 2026-03-11 00:00:00
C::ASM-004::PRT-0027 | MODULE | ASM-004 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2025-12-22 00:00:00 | 2026-03-17 00:00:00
C::ASM-005::PRT-0014 | MODULE | ASM-005 | Buck Weld Insert 6 inch | 1 | 60 | Blackwoods | 10 | Assembly BOM item | 2026-01-31 00:00:00 | 2026-03-11 00:00:00
C::ASM-005::PRT-0027 | MODULE | ASM-005 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2026-02-24 00:00:00 | 2026-03-16 00:00:00
C::ASM-006::PRT-0015 | MODULE | ASM-006 | Steel Bend Blank 6 inch | 1 | 40 | RS Components | 5 | Assembly BOM item | 2026-01-12 00:00:00 | 2026-03-14 00:00:00
C::ASM-006::PRT-0027 | MODULE | ASM-006 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2026-02-09 00:00:00 | 2026-03-16 00:00:00
C::ASM-007::PRT-0019 | MODULE | ASM-007 | Buck Weld Insert 8 inch | 1 | 30 | Austech | 14 | Assembly BOM item | 2026-02-13 00:00:00 | 2026-03-13 00:00:00
C::ASM-007::PRT-0027 | MODULE | ASM-007 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2025-12-17 00:00:00 | 2026-03-16 00:00:00
C::ASM-008::PRT-0020 | MODULE | ASM-008 | Steel Bend Blank 8 inch | 1 | 31 | Bosch Rexroth | 5 | Assembly BOM item | 2026-02-10 00:00:00 | 2026-03-14 00:00:00
C::ASM-008::PRT-0027 | MODULE | ASM-008 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2026-01-22 00:00:00 | 2026-03-12 00:00:00
C::ASM-009::PRT-0024 | MODULE | ASM-009 | Buck Weld Insert 10 inch | 1 | 41 | Festo | 21 | Assembly BOM item | 2025-12-06 00:00:00 | 2026-03-18 00:00:00
C::ASM-009::PRT-0027 | MODULE | ASM-009 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2025-12-13 00:00:00 | 2026-03-12 00:00:00 ¦ UnitPrice=199.00
C::ASM-010::PRT-0025 | MODULE | ASM-010 | Steel Bend Blank 10 inch | 1 | 19 | Austech | 5 | Assembly BOM item | 2026-01-18 00:00:00 | 2026-03-10 00:00:00
C::ASM-010::PRT-0027 | MODULE | ASM-010 | Bolt M12 Galv | 2 | 32 | OMRON | 21 | Assembly BOM item | 2025-11-29 00:00:00 | 2026-03-10 00:00:00
C::ASM-011::PRT-0029 | MODULE | ASM-011 | 12V Battery | 1 | 60 | Capral | 7 | Assembly BOM item | 2025-11-23 00:00:00 | 2026-03-10 00:00:00 ¦ UnitPrice=300.00
C::ASM-011::PRT-0030 | MODULE | ASM-011 | 60W Solar Panel | 1 | 45 | NHP | 5 | Assembly BOM item | 2025-12-13 00:00:00 | 2026-03-18 00:00:00 ¦ UnitPrice=199.00
C::ASM-011::PRT-0035 | MODULE | ASM-011 | GSM Modem | 1 | 30 | Festo | 7 | Assembly BOM item | 2025-12-28 00:00:00 | 2026-03-18 00:00:00
C::ASM-011::PRT-0036 | MODULE | ASM-011 | Antenna | 1 | 20 | SMC | 3 | Assembly BOM item | 2025-12-08 00:00:00 | 2026-03-14 00:00:00
C::ASM-011::PRT-0042 | MODULE | ASM-011 | Telemetry Cable Loom | 1 | 56 | Capral | 21 | Assembly BOM item | 2025-12-07 00:00:00 | 2026-03-10 00:00:00
C::ASM-012::PRT-0031 | MODULE | ASM-012 | Galv Angle 50x50 | 4 | 0 | SMC | 5 | Assembly BOM item | 2026-02-07 00:00:00 | 2026-03-16 00:00:00
C::ASM-012::PRT-0059 | MODULE | ASM-012 | Frame Base Plate | 1 | 46 | NHP | 3 | Assembly BOM item | 2026-01-01 00:00:00 | 2026-03-10 00:00:00
C::ASM-012::PRT-0060 | MODULE | ASM-012 | Galv Bolt Set | 1 | 5 | Bosch Rexroth | 10 | Assembly BOM item | 2026-01-27 00:00:00 | 2026-03-17 00:00:00
C::ASM-013::PRT-0032 | MODULE | ASM-013 | Solar Panel Bolt Kit | 1 | 49 | Austech | 10 | Assembly BOM item | 2026-01-06 00:00:00 | 2026-03-10 00:00:00
C::ASM-013::PRT-0060 | MODULE | ASM-013 | Galv Bolt Set | 1 | 5 | Bosch Rexroth | 10 | Assembly BOM item | 2025-12-13 00:00:00 | 2026-03-18 00:00:00 ¦ UnitPrice=199.00
C::ASM-014::PRT-0033 | MODULE | ASM-014 | Panel Enclosure | 1 | 6 | Bunnings Trade | 7 | Assembly BOM item | 2026-02-24 00:00:00 | 2026-03-12 00:00:00
C::ASM-014::PRT-0034 | MODULE | ASM-014 | PLC Relay | 1 | 24 | Bosch Rexroth | 3 | Assembly BOM item | 2026-01-20 00:00:00 | 2026-03-16 00:00:00 ¦ UnitPrice=99.00
C::ASM-014::PRT-0038 | MODULE | ASM-014 | DIN Rail | 1 | 25 | Bunnings Trade | 21 | Assembly BOM item | 2025-12-22 00:00:00 | 2026-03-10 00:00:00
C::ASM-014::PRT-0037 | MODULE | ASM-014 | Terminal Block | 10 | 20 | NHP | 10 | Assembly BOM item | 2025-11-22 00:00:00 | 2026-03-15 00:00:00
C::ASM-014::PRT-0039 | MODULE | ASM-014 | Circuit Breaker DC | 2 | 54 | Austech | 10 | Assembly BOM item | 2025-11-18 00:00:00 | 2026-03-13 00:00:00
C::ASM-014::PRT-0078 | MODULE | ASM-014 | Fuse Holder | 4 | 32 | Capral | 3 | Assembly BOM item | 2026-02-17 00:00:00 | 2026-03-17 00:00:00
C::ASM-014::PRT-0079 | MODULE | ASM-014 | Earth Lug | 2 | 2 | Bosch Rexroth | 10 | Assembly BOM item | 2026-01-21 00:00:00 | 2026-03-17 00:00:00
C::ASM-015::PRT-0076 | MODULE | ASM-015 | Label Set | 1 | 17 | Blackwoods | 14 | Assembly BOM item | 2026-01-01 00:00:00 | 2026-03-16 00:00:00
C::ASM-015::PRT-0064 | MODULE | ASM-015 | Cable Gland Kit | 1 | 15 | Blackwoods | 3 | Assembly BOM item | 2026-02-08 00:00:00 | 2026-03-13 00:00:00
C::ASM-016::PRT-0040 | MODULE | ASM-016 | Circuit Breaker AC | 2 | 52 | NHP | 10 | Assembly BOM item | 2025-12-24 00:00:00 | 2026-03-12 00:00:00
C::ASM-016::PRT-0046 | MODULE | ASM-016 | AC Contactor | 1 | 27 | Austech | 21 | Assembly BOM item | 2026-02-07 00:00:00 | 2026-03-13 00:00:00
C::ASM-016::PRT-0082 | MODULE | ASM-016 | Inverter AC | 1 | 8 | Austech | 21 | Assembly BOM item | 2026-01-12 00:00:00 | 2026-03-17 00:00:00
C::ASM-017::PRT-0083 | MODULE | ASM-017 | Battery Tray | 1 | 54 | RS Components | 7 | Assembly BOM item | 2025-12-29 00:00:00 | 2026-03-16 00:00:00
C::ASM-017::PRT-0029 | MODULE | ASM-017 | 12V Battery | 2 | 60 | Capral | 7 | Assembly BOM item | 2026-02-16 00:00:00 | 2026-03-14 00:00:00 ¦ UnitPrice=56.00
C::ASM-017::PRT-0048 | MODULE | ASM-017 | Battery Isolator | 1 | 31 | OMRON | 21 | Assembly BOM item | 2025-12-30 00:00:00 | 2026-03-16 00:00:00
C::ASM-018::PRT-0049 | MODULE | ASM-018 | Changeover Switch | 1 | 59 | Bunnings Trade | 3 | Assembly BOM item | 2025-11-21 00:00:00 | 2026-03-14 00:00:00
C::ASM-018::PRT-0040 | MODULE | ASM-018 | Circuit Breaker AC | 1 | 52 | NHP | 10 | Assembly BOM item | 2026-01-19 00:00:00 | 2026-03-13 00:00:00
C::ASM-018::PRT-0039 | MODULE | ASM-018 | Circuit Breaker DC | 1 | 54 | Austech | 10 | Assembly BOM item | 2025-11-26 00:00:00 | 2026-03-11 00:00:00
C::ASM-019::PRT-0050 | MODULE | ASM-019 | Pontoon Float | 4 | 16 | Bosch Rexroth | 5 | Assembly BOM item | 2025-11-19 00:00:00 | 2026-03-11 00:00:00
C::ASM-019::PRT-0090 | MODULE | ASM-019 | Pontoon Deck Plate | 2 | 46 | Bosch Rexroth | 10 | Assembly BOM item | 2026-02-21 00:00:00 | 2026-03-17 00:00:00
C::ASM-019::PRT-0092 | MODULE | ASM-019 | Shackle Set | 2 | 19 | OMRON | 3 | Assembly BOM item | 2026-02-09 00:00:00 | 2026-03-16 00:00:00
C::ASM-020::PRT-0074 | MODULE | ASM-020 | Galv Channel 100x50 | 4 | 42 | Capral | 3 | Assembly BOM item | 2026-01-06 00:00:00 | 2026-03-12 00:00:00
C::ASM-020::PRT-0060 | MODULE | ASM-020 | Galv Bolt Set | 2 | 5 | Bosch Rexroth | 10 | Assembly BOM item | 2026-01-12 00:00:00 | 2026-03-11 00:00:00
C::ASM-020::PRT-0061 | MODULE | ASM-020 | Pump Mount Plate | 1 | 0 | Austech | 14 | Assembly BOM item | 2025-11-21 00:00:00 | 2026-03-12 00:00:00
C::ASM-021::PRT-0051 | MODULE | ASM-021 | Winch 12V | 1 | 33 | Bosch Rexroth | 14 | Assembly BOM item | 2026-02-16 00:00:00 | 2026-03-10 00:00:00 ¦ UnitPrice=56.00
C::ASM-021::PRT-0072 | MODULE | ASM-021 | Winch Cable | 1 | 28 | Bunnings Trade | 5 | Assembly BOM item | 2026-02-14 00:00:00 | 2026-03-14 00:00:00
C::ASM-021::PRT-0073 | MODULE | ASM-021 | Bearing Block | 2 | 32 | SMC | 5 | Assembly BOM item | 2026-01-20 00:00:00 | 2026-03-12 00:00:00 ¦ UnitPrice=99.00
C::ASM-021::PRT-0093 | MODULE | ASM-021 | U-Bolt 12mm | 4 | 36 | Bosch Rexroth | 10 | Assembly BOM item | 2026-02-02 00:00:00 | 2026-03-12 00:00:00
C::ASM-022::PRT-0052 | MODULE | ASM-022 | Guide Rail | 2 | 39 | OMRON | 7 | Assembly BOM item | 2025-12-16 00:00:00 | 2026-03-13 00:00:00
C::ASM-022::PRT-0094 | MODULE | ASM-022 | Pump Guide Wheel | 2 | 45 | Bosch Rexroth | 21 | Assembly BOM item | 2026-02-20 00:00:00 | 2026-03-15 00:00:00
C::ASM-022::PRT-0027 | MODULE | ASM-022 | Bolt M12 Galv | 8 | 32 | OMRON | 21 | Assembly BOM item | 2026-01-20 00:00:00 | 2026-03-14 00:00:00 ¦ UnitPrice=99.00
C::ASM-023::PRT-0054 | MODULE | ASM-023 | Dust Fan | 1 | 31 | Blackwoods | 7 | Assembly BOM item | 2026-02-11 00:00:00 | 2026-03-12 00:00:00
C::ASM-023::PRT-0081 | MODULE | ASM-023 | Motor Starter | 1 | 41 | Bosch Rexroth | 21 | Assembly BOM item | 2025-12-10 00:00:00 | 2026-03-12 00:00:00
C::ASM-023::PRT-0061 | MODULE | ASM-023 | Pump Mount Plate | 1 | 0 | Austech | 14 | Assembly BOM item | 2026-02-16 00:00:00 | 2026-03-10 00:00:00 ¦ UnitPrice=56.00
C::ASM-024::PRT-0055 | MODULE | ASM-024 | Spray Nozzle | 6 | 10 | SMC | 3 | Assembly BOM item | 2026-02-02 00:00:00 | 2026-03-17 00:00:00
C::ASM-024::PRT-0089 | MODULE | ASM-024 | Spray Bar Clamp | 6 | 7 | Bunnings Trade | 21 | Assembly BOM item | 2025-11-21 00:00:00 | 2026-03-13 00:00:00
C::ASM-024::PRT-0056 | MODULE | ASM-024 | Water Hose Reel | 1 | 37 | RS Components | 21 | Assembly BOM item | 2026-02-23 00:00:00 | 2026-03-13 00:00:00
C::ASM-025::PRT-0085 | MODULE | ASM-025 | Weatherproof Antenna Bracket | 1 | 51 | Capral | 5 | Assembly BOM item | 2026-02-18 00:00:00 | 2026-03-17 00:00:00
C::ASM-025::PRT-0086 | MODULE | ASM-025 | Stainless Clamp Kit | 2 | 5 | Bunnings Trade | 10 | Assembly BOM item | 2026-02-11 00:00:00 | 2026-03-16 00:00:00
C::ASM-026::PRT-0077 | MODULE | ASM-026 | Solar Regulator | 1 | 32 | RS Components | 7 | Assembly BOM item | 2025-11-19 00:00:00 | 2026-03-14 00:00:00
C::ASM-026::PRT-0037 | MODULE | ASM-026 | Terminal Block | 6 | 20 | NHP | 10 | Assembly BOM item | 2025-12-27 00:00:00 | 2026-03-13 00:00:00
C::ASM-026::PRT-0039 | MODULE | ASM-026 | Circuit Breaker DC | 2 | 54 | Austech | 10 | Assembly BOM item | 2026-01-08 00:00:00 | 2026-03-10 00:00:00
C::ASM-026::PRT-0076 | MODULE | ASM-026 | Label Set | 1 | 17 | Blackwoods | 14 | Assembly BOM item | 2025-12-10 00:00:00 | 2026-03-13 00:00:00
C::ASM-027::PRT-0031 | MODULE | ASM-027 | Galv Angle 50x50 | 6 | 0 | SMC | 5 | Assembly BOM item | 2025-12-14 00:00:00 | 2026-03-12 00:00:00
C::ASM-027::PRT-0059 | MODULE | ASM-027 | Frame Base Plate | 1 | 46 | NHP | 3 | Assembly BOM item | 2026-02-14 00:00:00 | 2026-03-13 00:00:00
C::ASM-027::PRT-0075 | MODULE | ASM-027 | Control Panel Door | 1 | 21 | Bosch Rexroth | 7 | Assembly BOM item | 2026-01-03 00:00:00 | 2026-03-10 00:00:00
C::ASM-028::PRT-0061 | MODULE | ASM-028 | Pump Mount Plate | 1 | 0 | Austech | 14 | Assembly BOM item | 2025-12-03 00:00:00 | 2026-03-13 00:00:00
C::ASM-028::PRT-0068 | MODULE | ASM-028 | Pump 4 inch | 1 | 44 | Blackwoods | 3 | Assembly BOM item | 2025-12-14 00:00:00 | 2026-03-16 00:00:00
C::ASM-028::PRT-0087 | MODULE | ASM-028 | Rubber Mount | 4 | 57 | Blackwoods | 21 | Assembly BOM item | 2026-01-20 00:00:00 | 2026-03-15 00:00:00 ¦ UnitPrice=99.00
C::ASM-028::PRT-0070 | MODULE | ASM-028 | Flow Meter | 1 | 57 | Bunnings Trade | 10 | Assembly BOM item | 2025-11-28 00:00:00 | 2026-03-11 00:00:00
C::ASM-029::PRT-0065 | MODULE | ASM-029 | Poly Pipe 50mm 6 meters | 1 | 41 | Capral | 3 | Assembly BOM item | 2025-11-20 00:00:00 | 2026-03-15 00:00:00
C::ASM-029::PRT-0071 | MODULE | ASM-029 | Poly Float Arm | 1 | 53 | SMC | 5 | Assembly BOM item | 2026-02-22 00:00:00 | 2026-03-15 00:00:00
C::ASM-029::PRT-0086 | MODULE | ASM-029 | Stainless Clamp Kit | 2 | 5 | Bunnings Trade | 10 | Assembly BOM item | 2026-01-03 00:00:00 | 2026-03-18 00:00:00
C::ASM-030::PRT-0057 | MODULE | ASM-030 | Tank Level Sensor | 1 | 26 | OMRON | 21 | Assembly BOM item | 2026-01-11 00:00:00 | 2026-03-11 00:00:00
C::ASM-030::PRT-0042 | MODULE | ASM-030 | Telemetry Cable Loom | 1 | 56 | Capral | 21 | Assembly BOM item | 2025-12-31 00:00:00 | 2026-03-14 00:00:00
C::ASM-030::PRT-0084 | MODULE | ASM-030 | Wireless Gateway | 1 | 13 | Capral | 3 | Assembly BOM item | 2025-11-28 00:00:00 | 2026-03-17 00:00:00
C::ASM-031::PRT-0070 | MODULE | ASM-031 | Flow Meter | 1 | 57 | Bunnings Trade | 10 | Assembly BOM item | 2026-02-01 00:00:00 | 2026-03-13 00:00:00
C::ASM-031::PRT-0033 | MODULE | ASM-031 | Panel Enclosure | 1 | 6 | Bunnings Trade | 7 | Assembly BOM item | 2026-01-21 00:00:00 | 2026-03-13 00:00:00
C::ASM-031::PRT-0037 | MODULE | ASM-031 | Terminal Block | 6 | 20 | NHP | 10 | Assembly BOM item | 2025-11-18 00:00:00 | 2026-03-10 00:00:00
C::ASM-031::PRT-0063 | MODULE | ASM-031 | Control Panel Backplate | 1 | 37 | NHP | 7 | Assembly BOM item | 2026-02-12 00:00:00 | 2026-03-18 00:00:00
C::ASM-032::PRT-0033 | MODULE | ASM-032 | Panel Enclosure | 1 | 6 | Bunnings Trade | 7 | Assembly BOM item | 2025-11-26 00:00:00 | 2026-03-18 00:00:00
C::ASM-032::PRT-0034 | MODULE | ASM-032 | PLC Relay | 1 | 24 | Bosch Rexroth | 3 | Assembly BOM item | 2026-01-22 00:00:00 | 2026-03-11 00:00:00
C::ASM-032::PRT-0081 | MODULE | ASM-032 | Motor Starter | 1 | 41 | Bosch Rexroth | 21 | Assembly BOM item | 2026-01-02 00:00:00 | 2026-03-14 00:00:00
C::ASM-032::PRT-0041 | MODULE | ASM-032 | 24V PSU | 1 | 12 | Bunnings Trade | 21 | Assembly BOM item | 2026-02-03 00:00:00 | 2026-03-11 00:00:00 ¦ UnitPrice=59.00
C::ASM-032::PRT-0076 | MODULE | ASM-032 | Label Set | 1 | 17 | Blackwoods | 14 | Assembly BOM item | 2026-02-11 00:00:00 | 2026-03-17 00:00:00
C::ASM-033::PRT-0030 | MODULE | ASM-033 | 60W Solar Panel | 1 | 45 | NHP | 5 | Assembly BOM item | 2026-01-30 00:00:00 | 2026-03-14 00:00:00 ¦ UnitPrice=896.00
C::ASM-033::PRT-0032 | MODULE | ASM-033 | Solar Panel Bolt Kit | 1 | 49 | Austech | 10 | Assembly BOM item | 2026-01-27 00:00:00 | 2026-03-11 00:00:00
C::ASM-033::PRT-0085 | MODULE | ASM-033 | Weatherproof Antenna Bracket | 1 | 51 | Capral | 5 | Assembly BOM item | 2026-02-08 00:00:00 | 2026-03-10 00:00:00
C::ASM-034::PRT-0051 | MODULE | ASM-034 | Winch 12V | 1 | 33 | Bosch Rexroth | 14 | Assembly BOM item | 2025-12-06 00:00:00 | 2026-03-12 00:00:00
C::ASM-034::PRT-0048 | MODULE | ASM-034 | Battery Isolator | 1 | 31 | OMRON | 21 | Assembly BOM item | 2026-01-29 00:00:00 | 2026-03-14 00:00:00
C::ASM-034::PRT-0063 | MODULE | ASM-034 | Control Panel Backplate | 1 | 37 | NHP | 7 | Assembly BOM item | 2026-01-24 00:00:00 | 2026-03-13 00:00:00
C::ASM-035::PRT-0033 | MODULE | ASM-035 | Panel Enclosure | 1 | 6 | Bunnings Trade | 7 | Assembly BOM item | 2026-01-04 00:00:00 | 2026-03-10 00:00:00
C::ASM-035::PRT-0034 | MODULE | ASM-035 | PLC Relay | 1 | 24 | Bosch Rexroth | 3 | Assembly BOM item | 2026-02-14 00:00:00 | 2026-03-18 00:00:00
C::ASM-035::PRT-0044 | MODULE | ASM-035 | Pressure Sensor | 1 | 40 | RS Components | 14 | Assembly BOM item | 2026-01-02 00:00:00 | 2026-03-14 00:00:00
C::ASM-035::PRT-0040 | MODULE | ASM-035 | Circuit Breaker AC | 1 | 52 | NHP | 10 | Assembly BOM item | 2026-02-04 00:00:00 | 2026-03-11 00:00:00
C::PROD-001::PRT-0001 | PRODUCT | PROD-001 | Pipe 2 inch 6 meters | 1 | 41 | NHP | 7 | Direct product item | 2025-12-18 00:00:00 | 2026-03-16 00:00:00
C::PROD-001::PRT-0002 | PRODUCT | PROD-001 | Stub 2 inch | 2 | 34 | Bunnings Trade | 14 | Direct product item | 2026-02-17 00:00:00 | 2026-03-13 00:00:00
C::PROD-001::PRT-0026 | PRODUCT | PROD-001 | Poly Hinge | 2 | 35 | Capral | 10 | Direct product item | 2026-01-15 00:00:00 | 2026-03-12 00:00:00
C::PROD-001::PRT-0027 | PRODUCT | PROD-001 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct product item | 2026-01-03 00:00:00 | 2026-03-18 00:00:00
C::PROD-001::PRT-0028 | PRODUCT | PROD-001 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct product item | 2026-03-05 00:00:00 | 2026-03-15 00:00:00
C::PROD-001::PRT-0003 | PRODUCT | PROD-001 | Flange 2 inch | 6 | 50 | SMC | 5 | Direct product item | 2025-12-19 00:00:00 | 2026-03-13 00:00:00
C::PROD-002::PRT-0006 | PRODUCT | PROD-002 | Pipe 4 inch 6 meters | 1 | 44 | Capral | 10 | Direct product item | 2025-12-30 00:00:00 | 2026-03-15 00:00:00
C::PROD-002::PRT-0007 | PRODUCT | PROD-002 | Stub 4 inch | 2 | 47 | Bosch Rexroth | 5 | Direct product item | 2026-02-20 00:00:00 | 2026-03-16 00:00:00
C::PROD-002::PRT-0026 | PRODUCT | PROD-002 | Poly Hinge | 2 | 35 | Capral | 10 | Direct product item | 2025-12-18 00:00:00 | 2026-03-13 00:00:00
C::PROD-002::PRT-0027 | PRODUCT | PROD-002 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct product item | 2025-12-20 00:00:00 | 2026-03-14 00:00:00
C::PROD-002::PRT-0028 | PRODUCT | PROD-002 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct product item | 2026-01-20 00:00:00 | 2026-03-16 00:00:00 ¦ UnitPrice=99.00
C::PROD-002::PRT-0008 | PRODUCT | PROD-002 | Flange 4 inch | 6 | 22 | SMC | 10 | Direct product item | 2026-01-03 00:00:00 | 2026-03-12 00:00:00
C::PROD-003::PRT-0011 | PRODUCT | PROD-003 | Pipe 6 inch 6 meters | 1 | 21 | RS Components | 5 | Direct product item | 2026-01-14 00:00:00 | 2026-03-18 00:00:00
C::PROD-003::PRT-0012 | PRODUCT | PROD-003 | Stub 6 inch | 2 | 12 | Bunnings Trade | 21 | Direct product item | 2026-01-05 00:00:00 | 2026-03-18 00:00:00
C::PROD-003::PRT-0026 | PRODUCT | PROD-003 | Poly Hinge | 2 | 35 | Capral | 10 | Direct product item | 2026-02-03 00:00:00 | 2026-03-12 00:00:00 ¦ UnitPrice=59.00
C::PROD-003::PRT-0027 | PRODUCT | PROD-003 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct product item | 2026-02-14 00:00:00 | 2026-03-14 00:00:00
C::PROD-003::PRT-0028 | PRODUCT | PROD-003 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct product item | 2026-02-02 00:00:00 | 2026-03-12 00:00:00
C::PROD-003::PRT-0013 | PRODUCT | PROD-003 | Flange 6 inch | 6 | 25 | RS Components | 10 | Direct product item | 2026-01-11 00:00:00 | 2026-03-14 00:00:00
C::PROD-004::PRT-0016 | PRODUCT | PROD-004 | Pipe 8 inch 6 meters | 1 | 30 | Bunnings Trade | 7 | Direct product item | 2026-01-28 00:00:00 | 2026-03-13 00:00:00
C::PROD-004::PRT-0017 | PRODUCT | PROD-004 | Stub 8 inch | 2 | 32 | Bosch Rexroth | 21 | Direct product item | 2026-03-08 00:00:00 | 2026-03-17 00:00:00
C::PROD-004::PRT-0026 | PRODUCT | PROD-004 | Poly Hinge | 2 | 35 | Capral | 10 | Direct product item | 2026-01-13 00:00:00 | 2026-03-17 00:00:00
C::PROD-004::PRT-0027 | PRODUCT | PROD-004 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct product item | 2026-01-31 00:00:00 | 2026-03-13 00:00:00
C::PROD-004::PRT-0028 | PRODUCT | PROD-004 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct product item | 2026-01-11 00:00:00 | 2026-03-18 00:00:00
C::PROD-004::PRT-0018 | PRODUCT | PROD-004 | Flange 8 inch | 6 | 21 | RS Components | 10 | Direct product item | 2025-12-24 00:00:00 | 2026-03-18 00:00:00
C::PROD-005::PRT-0021 | PRODUCT | PROD-005 | Pipe 10 inch 6 meters | 1 | 44 | NHP | 3 | Direct product item | 2025-12-28 00:00:00 | 2026-03-14 00:00:00
C::PROD-005::PRT-0022 | PRODUCT | PROD-005 | Stub 10 inch | 2 | 10 | Capral | 21 | Direct product item | 2026-02-05 00:00:00 | 2026-03-15 00:00:00
C::PROD-005::PRT-0026 | PRODUCT | PROD-005 | Poly Hinge | 2 | 35 | Capral | 10 | Direct product item | 2026-02-09 00:00:00 | 2026-03-14 00:00:00
C::PROD-005::PRT-0027 | PRODUCT | PROD-005 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct product item | 2025-12-27 00:00:00 | 2026-03-17 00:00:00
C::PROD-005::PRT-0028 | PRODUCT | PROD-005 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct product item | 2026-02-01 00:00:00 | 2026-03-13 00:00:00
C::PROD-005::PRT-0023 | PRODUCT | PROD-005 | Flange 10 inch | 6 | 55 | Bunnings Trade | 7 | Direct product item | 2026-01-11 00:00:00 | 2026-03-18 00:00:00
C::PROD-006::PRT-0044 | PRODUCT | PROD-006 | Pressure Sensor | 1 | 40 | RS Components | 14 | Direct product item | 2026-01-24 00:00:00 | 2026-03-16 00:00:00
C::PROD-006::PRT-0043 | PRODUCT | PROD-006 | Float Switch | 1 | 15 | Capral | 10 | Direct product item | 2026-01-11 00:00:00 | 2026-03-18 00:00:00
C::PROD-007::PRT-0043 | PRODUCT | PROD-007 | Float Switch | 1 | 15 | Capral | 10 | Direct product item | 2026-01-06 00:00:00 | 2026-03-16 00:00:00
C::PROD-008::PRT-0045 | PRODUCT | PROD-008 | Fuel Meter | 2 | 57 | SMC | 5 | Direct product item | 2025-12-27 00:00:00 | 2026-03-13 00:00:00
C::PROD-008::PRT-0070 | PRODUCT | PROD-008 | Flow Meter | 1 | 57 | Bunnings Trade | 10 | Direct product item | 2026-02-26 00:00:00 | 2026-03-16 00:00:00
C::PROD-009::PRT-0045 | PRODUCT | PROD-009 | Fuel Meter | 2 | 57 | SMC | 5 | Direct product item | 2026-01-23 00:00:00 | 2026-03-18 00:00:00
C::PROD-009::PRT-0029 | PRODUCT | PROD-009 | 12V Battery | 2 | 60 | Capral | 7 | Direct product item | 2026-01-20 00:00:00 | 2026-03-14 00:00:00 ¦ UnitPrice=99.00
C::PROD-010::PRT-0045 | PRODUCT | PROD-010 | Fuel Meter | 2 | 57 | SMC | 5 | Direct product item | 2026-01-08 00:00:00 | 2026-03-14 00:00:00
C::PROD-011::PRT-0068 | PRODUCT | PROD-011 | Pump 4 inch | 1 | 44 | Blackwoods | 3 | Direct product item | 2026-02-01 00:00:00 | 2026-03-13 00:00:00
C::PROD-011::PRT-0092 | PRODUCT | PROD-011 | Shackle Set | 2 | 19 | OMRON | 3 | Direct product item | 2026-02-05 00:00:00 | 2026-03-14 00:00:00
C::PROD-012::PRT-0067 | PRODUCT | PROD-012 | Pump 2 inch | 1 | 27 | OMRON | 14 | Direct product item | 2025-12-18 00:00:00 | 2026-03-15 00:00:00
C::PROD-012::PRT-0065 | PRODUCT | PROD-012 | Poly Pipe 50mm 6 meters | 1 | 41 | Capral | 3 | Direct product item | 2026-01-08 00:00:00 | 2026-03-17 00:00:00
C::PROD-013::PRT-0056 | PRODUCT | PROD-013 | Water Hose Reel | 1 | 37 | RS Components | 21 | Direct product item | 2026-03-07 00:00:00 | 2026-03-12 00:00:00
C::PROD-013::PRT-0044 | PRODUCT | PROD-013 | Pressure Sensor | 1 | 40 | RS Components | 14 | Direct product item | 2026-02-11 00:00:00 | 2026-03-13 00:00:00
C::PROD-014::PRT-0084 | PRODUCT | PROD-014 | Wireless Gateway | 1 | 13 | Capral | 3 | Direct product item | 2026-02-05 00:00:00 | 2026-03-12 00:00:00
C::PROD-015::PRT-0030 | PRODUCT | PROD-015 | 60W Solar Panel | 2 | 45 | NHP | 5 | Direct product item | 2026-01-19 00:00:00 | 2026-03-13 00:00:00
C::PROD-015::PRT-0044 | PRODUCT | PROD-015 | Pressure Sensor | 1 | 40 | RS Components | 14 | Direct product item | 2025-12-29 00:00:00 | 2026-03-18 00:00:00
C::PROD-016::PRT-0075 | PRODUCT | PROD-016 | Control Panel Door | 1 | 21 | Bosch Rexroth | 7 | Direct product item | 2026-01-08 00:00:00 | 2026-03-16 00:00:00
C::PROD-016::PRT-0080 | PRODUCT | PROD-016 | Panel Cooling Fan | 1 | 30 | Bosch Rexroth | 10 | Direct product item | 2026-01-04 00:00:00 | 2026-03-18 00:00:00
C::PROD-017::PRT-0068 | PRODUCT | PROD-017 | Pump 4 inch | 1 | 44 | Blackwoods | 3 | Direct product item | 2026-02-15 00:00:00 | 2026-03-15 00:00:00
C::PROD-018::PRT-0066 | PRODUCT | PROD-018 | Poly Pipe 80mm 6 meters | 1 | 38 | Austech | 7 | Direct product item | 2026-02-15 00:00:00 | 2026-03-12 00:00:00
C::PROD-019::PRT-0091 | PRODUCT | PROD-019 | Poly Tank 200L | 1 | 16 | Festo | 21 | Direct product item | 2026-01-07 00:00:00 | 2026-03-15 00:00:00
C::PROD-020::PRT-0070 | PRODUCT | PROD-020 | Flow Meter | 1 | 57 | Bunnings Trade | 10 | Direct product item | 2026-01-17 00:00:00 | 2026-03-17 00:00:00
C::PROD-020::PRT-0045 | PRODUCT | PROD-020 | Fuel Meter | 1 | 57 | SMC | 5 | Direct product item | 2026-01-06 00:00:00 | 2026-03-14 00:00:00
C::ORD-001::PRT-0001 | PROJECT | ORD-001 | Pipe 2 inch 6 meters | 1 | 41 | NHP | 7 | Direct order item | 2025-12-18 00:00:00 | 2026-03-16 00:00:00
C::ORD-001::PRT-0002 | PROJECT | ORD-001 | Stub 2 inch | 2 | 34 | Bunnings Trade | 14 | Direct order item | 2026-02-17 00:00:00 | 2026-03-13 00:00:00
C::ORD-001::PRT-0026 | PROJECT | ORD-001 | Poly Hinge | 2 | 35 | Capral | 10 | Direct order item | 2026-01-15 00:00:00 | 2026-03-12 00:00:00
C::ORD-001::PRT-0027 | PROJECT | ORD-001 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct order item | 2026-01-03 00:00:00 | 2026-03-18 00:00:00
C::ORD-001::PRT-0028 | PROJECT | ORD-001 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct order item | 2026-03-05 00:00:00 | 2026-03-15 00:00:00
C::ORD-001::PRT-0003 | PROJECT | ORD-001 | Flange 2 inch | 6 | 50 | SMC | 5 | Direct order item | 2025-12-19 00:00:00 | 2026-03-13 00:00:00
C::ORD-002::PRT-0006 | PROJECT | ORD-002 | Pipe 4 inch 6 meters | 1 | 44 | Capral | 10 | Direct order item | 2025-12-30 00:00:00 | 2026-03-15 00:00:00
C::ORD-002::PRT-0007 | PROJECT | ORD-002 | Stub 4 inch | 2 | 47 | Bosch Rexroth | 5 | Direct order item | 2026-02-20 00:00:00 | 2026-03-16 00:00:00
C::ORD-002::PRT-0026 | PROJECT | ORD-002 | Poly Hinge | 2 | 35 | Capral | 10 | Direct order item | 2025-12-18 00:00:00 | 2026-03-13 00:00:00
C::ORD-002::PRT-0027 | PROJECT | ORD-002 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct order item | 2025-12-20 00:00:00 | 2026-03-14 00:00:00
C::ORD-002::PRT-0028 | PROJECT | ORD-002 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct order item | 2026-01-20 00:00:00 | 2026-03-16 00:00:00 ¦ UnitPrice=99.00
C::ORD-002::PRT-0008 | PROJECT | ORD-002 | Flange 4 inch | 6 | 22 | SMC | 10 | Direct order item | 2026-01-03 00:00:00 | 2026-03-12 00:00:00
C::ORD-003::PRT-0011 | PROJECT | ORD-003 | Pipe 6 inch 6 meters | 1 | 21 | RS Components | 5 | Direct order item | 2026-01-14 00:00:00 | 2026-03-18 00:00:00
C::ORD-003::PRT-0012 | PROJECT | ORD-003 | Stub 6 inch | 2 | 12 | Bunnings Trade | 21 | Direct order item | 2026-01-05 00:00:00 | 2026-03-18 00:00:00
C::ORD-003::PRT-0026 | PROJECT | ORD-003 | Poly Hinge | 2 | 35 | Capral | 10 | Direct order item | 2026-02-03 00:00:00 | 2026-03-12 00:00:00 ¦ UnitPrice=59.00
C::ORD-003::PRT-0027 | PROJECT | ORD-003 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct order item | 2026-02-14 00:00:00 | 2026-03-14 00:00:00
C::ORD-003::PRT-0028 | PROJECT | ORD-003 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct order item | 2026-02-02 00:00:00 | 2026-03-12 00:00:00
C::ORD-003::PRT-0013 | PROJECT | ORD-003 | Flange 6 inch | 6 | 25 | RS Components | 10 | Direct order item | 2026-01-11 00:00:00 | 2026-03-14 00:00:00
C::ORD-004::PRT-0016 | PROJECT | ORD-004 | Pipe 8 inch 6 meters | 1 | 30 | Bunnings Trade | 7 | Direct order item | 2026-01-28 00:00:00 | 2026-03-13 00:00:00
C::ORD-004::PRT-0017 | PROJECT | ORD-004 | Stub 8 inch | 2 | 32 | Bosch Rexroth | 21 | Direct order item | 2026-03-08 00:00:00 | 2026-03-17 00:00:00
C::ORD-004::PRT-0026 | PROJECT | ORD-004 | Poly Hinge | 2 | 35 | Capral | 10 | Direct order item | 2026-01-13 00:00:00 | 2026-03-17 00:00:00
C::ORD-004::PRT-0027 | PROJECT | ORD-004 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct order item | 2026-01-31 00:00:00 | 2026-03-13 00:00:00
C::ORD-004::PRT-0028 | PROJECT | ORD-004 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct order item | 2026-01-11 00:00:00 | 2026-03-18 00:00:00
C::ORD-004::PRT-0018 | PROJECT | ORD-004 | Flange 8 inch | 6 | 21 | RS Components | 10 | Direct order item | 2025-12-24 00:00:00 | 2026-03-18 00:00:00
C::ORD-005::PRT-0021 | PROJECT | ORD-005 | Pipe 10 inch 6 meters | 1 | 44 | NHP | 3 | Direct order item | 2025-12-28 00:00:00 | 2026-03-14 00:00:00
C::ORD-005::PRT-0022 | PROJECT | ORD-005 | Stub 10 inch | 2 | 10 | Capral | 21 | Direct order item | 2026-02-05 00:00:00 | 2026-03-15 00:00:00
C::ORD-005::PRT-0026 | PROJECT | ORD-005 | Poly Hinge | 2 | 35 | Capral | 10 | Direct order item | 2026-02-09 00:00:00 | 2026-03-14 00:00:00
C::ORD-005::PRT-0027 | PROJECT | ORD-005 | Bolt M12 Galv | 10 | 32 | OMRON | 21 | Direct order item | 2025-12-27 00:00:00 | 2026-03-17 00:00:00
C::ORD-005::PRT-0028 | PROJECT | ORD-005 | Lug 12mm | 6 | 19 | Bosch Rexroth | 7 | Direct order item | 2026-02-01 00:00:00 | 2026-03-13 00:00:00
C::ORD-005::PRT-0023 | PROJECT | ORD-005 | Flange 10 inch | 6 | 55 | Bunnings Trade | 7 | Direct order item | 2026-01-11 00:00:00 | 2026-03-18 00:00:00
C::ORD-006::PRT-0044 | PROJECT | ORD-006 | Pressure Sensor | 1 | 40 | RS Components | 14 | Direct order item | 2026-01-24 00:00:00 | 2026-03-16 00:00:00
C::ORD-006::PRT-0043 | PROJECT | ORD-006 | Float Switch | 1 | 15 | Capral | 10 | Direct order item | 2026-01-11 00:00:00 | 2026-03-18 00:00:00
C::ORD-007::PRT-0043 | PROJECT | ORD-007 | Float Switch | 1 | 15 | Capral | 10 | Direct order item | 2026-01-06 00:00:00 | 2026-03-16 00:00:00
C::ORD-008::PRT-0045 | PROJECT | ORD-008 | Fuel Meter | 2 | 57 | SMC | 5 | Direct order item | 2025-12-27 00:00:00 | 2026-03-13 00:00:00
C::ORD-008::PRT-0070 | PROJECT | ORD-008 | Flow Meter | 1 | 57 | Bunnings Trade | 10 | Direct order item | 2026-02-26 00:00:00 | 2026-03-16 00:00:00
C::PROD-003::AC_CONTACTOR::123212243277 | PRODUCT | PROD-003 | AC Contactor | 1 | 0 | Austech | 0 |  | 2026-02-07 00:00:00 | 2026-03-13 00:00:00 | 2026-03-18 12:32:12 | 2026-03-18 12:32:12
C::PROD-014::60W_SOLAR_PANEL::155741711019 | PRODUCT | PROD-014 | 60W Solar Panel | 1 | 0 | NHP | 0 |  | 2025-12-13 00:00:00 | 2026-03-18 00:00:00 ¦ UnitPrice=199.00 | 2026-03-18 15:57:41 | 2026-03-18 15:57:41
C::P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC::24V_PSU::162528335687 | PRODUCT | P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC | 24V PSU | 1 | 12 | Bunnings Trade | 0 |  | 2026-02-03 00:00:00 | 2026-03-11 00:00:00 ¦ UnitPrice=59.00 | 2026-03-18 16:25:28 | 2026-03-18 16:25:28
C::P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC::12V_BATTERY::162537364010 | PRODUCT | P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC | 12V Battery | 1 | 12 | Bunnings Trade | 0 |  | 2025-11-23 00:00:00 | 2026-03-11 00:00:00 ¦ UnitPrice=59.00 | 2026-03-18 16:25:37 | 2026-03-18 16:25:37

## Documents
DocID | OwnerType | OwnerCode | SectionName | DocName | DocType | FilePath | InstructionText | AddedOn | UpdatedOn
D::ASM-001 | MODULE | ASM-001 | Assembly Pack | ASM-001_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-001_assembly_pack.pdf | Assembly build notes | 2026-03-04 00:00:00 | 2026-03-14 00:00:00
D::ASM-002 | MODULE | ASM-002 | Assembly Pack | ASM-002_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-002_assembly_pack.pdf | Assembly build notes | 2026-02-14 00:00:00 | 2026-03-15 00:00:00
D::ASM-003 | MODULE | ASM-003 | Assembly Pack | ASM-003_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-003_assembly_pack.pdf | Assembly build notes | 2026-02-16 00:00:00 | 2026-03-15 00:00:00
D::ASM-004 | MODULE | ASM-004 | Assembly Pack | ASM-004_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-004_assembly_pack.pdf | Assembly build notes | 2026-01-30 00:00:00 | 2026-03-13 00:00:00
D::ASM-005 | MODULE | ASM-005 | Assembly Pack | ASM-005_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-005_assembly_pack.pdf | Assembly build notes | 2026-02-12 00:00:00 | 2026-03-17 00:00:00
D::ASM-006 | MODULE | ASM-006 | Assembly Pack | ASM-006_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-006_assembly_pack.pdf | Assembly build notes | 2026-03-04 00:00:00 | 2026-03-16 00:00:00
D::ASM-007 | MODULE | ASM-007 | Assembly Pack | ASM-007_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-007_assembly_pack.pdf | Assembly build notes | 2026-03-07 00:00:00 | 2026-03-18 00:00:00
D::ASM-008 | MODULE | ASM-008 | Assembly Pack | ASM-008_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-008_assembly_pack.pdf | Assembly build notes | 2026-03-03 00:00:00 | 2026-03-18 00:00:00
D::ASM-009 | MODULE | ASM-009 | Assembly Pack | ASM-009_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-009_assembly_pack.pdf | Assembly build notes | 2026-02-23 00:00:00 | 2026-03-15 00:00:00
D::ASM-010 | MODULE | ASM-010 | Assembly Pack | ASM-010_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-010_assembly_pack.pdf | Assembly build notes | 2026-02-03 00:00:00 | 2026-03-17 00:00:00
D::ASM-011 | MODULE | ASM-011 | Assembly Pack | ASM-011_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-011_assembly_pack.pdf | Assembly build notes | 2026-03-02 00:00:00 | 2026-03-16 00:00:00
D::ASM-012 | MODULE | ASM-012 | Assembly Pack | ASM-012_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-012_assembly_pack.pdf | Assembly build notes | 2026-03-01 00:00:00 | 2026-03-15 00:00:00
D::ASM-013 | MODULE | ASM-013 | Assembly Pack | ASM-013_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-013_assembly_pack.pdf | Assembly build notes | 2026-03-03 00:00:00 | 2026-03-16 00:00:00
D::ASM-014 | MODULE | ASM-014 | Assembly Pack | ASM-014_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-014_assembly_pack.pdf | Assembly build notes | 2026-02-28 00:00:00 | 2026-03-16 00:00:00
D::ASM-015 | MODULE | ASM-015 | Assembly Pack | ASM-015_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-015_assembly_pack.pdf | Assembly build notes | 2026-03-01 00:00:00 | 2026-03-16 00:00:00
D::ASM-016 | MODULE | ASM-016 | Assembly Pack | ASM-016_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-016_assembly_pack.pdf | Assembly build notes | 2026-03-05 00:00:00 | 2026-03-13 00:00:00
D::ASM-017 | MODULE | ASM-017 | Assembly Pack | ASM-017_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-017_assembly_pack.pdf | Assembly build notes | 2026-02-04 00:00:00 | 2026-03-18 00:00:00
D::ASM-018 | MODULE | ASM-018 | Assembly Pack | ASM-018_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-018_assembly_pack.pdf | Assembly build notes | 2026-02-18 00:00:00 | 2026-03-13 00:00:00
D::ASM-019 | MODULE | ASM-019 | Assembly Pack | ASM-019_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-019_assembly_pack.pdf | Assembly build notes | 2026-02-06 00:00:00 | 2026-03-14 00:00:00
D::ASM-020 | MODULE | ASM-020 | Assembly Pack | ASM-020_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-020_assembly_pack.pdf | Assembly build notes | 2026-02-11 00:00:00 | 2026-03-17 00:00:00
D::ASM-021 | MODULE | ASM-021 | Assembly Pack | ASM-021_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-021_assembly_pack.pdf | Assembly build notes | 2026-02-24 00:00:00 | 2026-03-17 00:00:00
D::ASM-022 | MODULE | ASM-022 | Assembly Pack | ASM-022_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-022_assembly_pack.pdf | Assembly build notes | 2026-02-05 00:00:00 | 2026-03-18 00:00:00
D::ASM-023 | MODULE | ASM-023 | Assembly Pack | ASM-023_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-023_assembly_pack.pdf | Assembly build notes | 2026-02-04 00:00:00 | 2026-03-15 00:00:00
D::ASM-024 | MODULE | ASM-024 | Assembly Pack | ASM-024_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-024_assembly_pack.pdf | Assembly build notes | 2026-01-29 00:00:00 | 2026-03-17 00:00:00
D::ASM-025 | MODULE | ASM-025 | Assembly Pack | ASM-025_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-025_assembly_pack.pdf | Assembly build notes | 2026-01-28 00:00:00 | 2026-03-15 00:00:00
D::ASM-026 | MODULE | ASM-026 | Assembly Pack | ASM-026_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-026_assembly_pack.pdf | Assembly build notes | 2026-03-05 00:00:00 | 2026-03-16 00:00:00
D::ASM-027 | MODULE | ASM-027 | Assembly Pack | ASM-027_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-027_assembly_pack.pdf | Assembly build notes | 2026-02-20 00:00:00 | 2026-03-17 00:00:00
D::ASM-028 | MODULE | ASM-028 | Assembly Pack | ASM-028_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-028_assembly_pack.pdf | Assembly build notes | 2026-02-21 00:00:00 | 2026-03-16 00:00:00
D::ASM-029 | MODULE | ASM-029 | Assembly Pack | ASM-029_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-029_assembly_pack.pdf | Assembly build notes | 2026-01-27 00:00:00 | 2026-03-17 00:00:00
D::ASM-030 | MODULE | ASM-030 | Assembly Pack | ASM-030_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-030_assembly_pack.pdf | Assembly build notes | 2026-03-01 00:00:00 | 2026-03-13 00:00:00
D::ASM-031 | MODULE | ASM-031 | Assembly Pack | ASM-031_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-031_assembly_pack.pdf | Assembly build notes | 2026-02-10 00:00:00 | 2026-03-14 00:00:00
D::ASM-032 | MODULE | ASM-032 | Assembly Pack | ASM-032_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-032_assembly_pack.pdf | Assembly build notes | 2026-02-26 00:00:00 | 2026-03-15 00:00:00
D::ASM-033 | MODULE | ASM-033 | Assembly Pack | ASM-033_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-033_assembly_pack.pdf | Assembly build notes | 2026-02-14 00:00:00 | 2026-03-13 00:00:00
D::ASM-034 | MODULE | ASM-034 | Assembly Pack | ASM-034_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-034_assembly_pack.pdf | Assembly build notes | 2026-02-01 00:00:00 | 2026-03-16 00:00:00
D::ASM-035 | MODULE | ASM-035 | Assembly Pack | ASM-035_assembly_pack.pdf | PDF | C:\Liquimech\docs\assemblies\ASM-035_assembly_pack.pdf | Assembly build notes | 2026-02-22 00:00:00 | 2026-03-16 00:00:00

## Products
ProductCode | QuoteRef | ProductName | Description | Revision | Status | CreatedOn | UpdatedOn
PROD-001 | SP-2 | Standpipe 2 inch | Standpipe package using 2 inch pipe, fabricated bends and direct loose items. | R0 | Released | 2026-02-14 00:00:00 | 2026-03-13 00:00:00
PROD-002 | SP-4 | Standpipe 4 inch | Standpipe package using 4 inch pipe, fabricated bends and direct loose items. | R1 | Released | 2026-01-24 00:00:00 | 2026-03-12 00:00:00
PROD-003 | SP-6 | Standpipe 6 inch | Standpipe package using 6 inch pipe, fabricated bends and direct loose items. | R2 | Released | 2026-01-04 00:00:00 | 2026-03-13 00:00:00
PROD-004 | SP-8 | Standpipe 8 inch | Standpipe package using 8 inch pipe, fabricated bends and direct loose items. | R0 | Released | 2026-01-30 00:00:00 | 2026-03-15 00:00:00
PROD-005 | SP-10 | Standpipe 10 inch | Standpipe package using 10 inch pipe, fabricated bends and direct loose items. | R1 | Released | 2026-01-22 00:00:00 | 2026-03-17 00:00:00
PROD-006 | SWA-12V | Smart Water Access 12V | Solar telemetry water access package with framed solar and control panel. | R2 | Released | 2026-01-26 00:00:00 | 2026-03-12 00:00:00
PROD-007 | SWA-LITE | Smart Water Access Solar Lite | Reduced solar access solution. | R0 | Released | 2026-03-01 00:00:00 | 2026-03-13 00:00:00
PROD-008 | FMS-AC | Fuel Management System AC | AC powered fuel management panel and skid. | R1 | Released | 2026-01-03 00:00:00 | 2026-03-17 00:00:00
PROD-009 | FMS-DC | Fuel Management System DC | DC battery based fuel management skid. | R2 | Released | 2025-12-28 00:00:00 | 2026-03-18 00:00:00
PROD-010 | FMS-HYB | Fuel Management System Hybrid | Hybrid AC/DC fuel management system. | R0 | Released | 2025-12-20 00:00:00 | 2026-03-15 00:00:00
PROD-011 | PONT-NE | Pontoon Without Electric | Mechanical pontoon pump access with no electrical package. | R1 | Released | 2026-03-02 00:00:00 | 2026-03-18 00:00:00
PROD-012 | POLY-WINCH | Poly with Winch Pump Lifter | Poly float and winch pump lifting assembly. | R2 | Released | 2026-01-24 00:00:00 | 2026-03-18 00:00:00
PROD-013 | DSS-01 | Dust Suppression System | Dust suppression skid with spray manifold and control panel. | R0 | Released | 2026-01-07 00:00:00 | 2026-03-14 00:00:00
PROD-014 | TEL-RET | Telemetry Retrofit Kit | Retrofit telemetry upgrade kit. | R1 | Released | 2025-12-21 00:00:00 | 2026-03-18 00:00:00
PROD-015 | SBC-01 | Solar Bore Controller | Solar bore controller with mount and pump control panel. | R2 | Released | 2026-01-26 00:00:00 | 2026-03-13 00:00:00
PROD-016 | KIOSK-01 | Steel Frame Kiosk | Standalone steel kiosk enclosure with control panel. | R0 | Released | 2026-01-10 00:00:00 | 2026-03-16 00:00:00
PROD-017 | RPS-01 | Remote Pump Skid | Remote pump skid with telemetry and solar mount. | R1 | Released | 2026-01-02 00:00:00 | 2026-03-15 00:00:00
PROD-018 | PAP-01 | Poly Pipe Access Pod | Access pod for poly pipe and sensor loom. | R2 | Released | 2026-02-23 00:00:00 | 2026-03-15 00:00:00
PROD-019 | STMS-01 | Smart Tank Monitoring Station | Tank monitoring station with telemetry, frame and control. | R0 | Released | 2026-01-09 00:00:00 | 2026-03-18 00:00:00
PROD-020 | VMP-01 | Valve & Meter Panel | Standalone valve and metering panel. | R1 | Released | 2026-01-15 00:00:00 | 2026-03-17 00:00:00
P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC | FMS-DC | Fuel Management System DC | DC battery based fuel management skid. | R2 | Released | 2025-12-28 00:00:00 | 2026-03-18 12:14:59
P_FMS-HYB_FUEL_MANAGEMENT_SYSTEM_HYBRID_V1 | FMS-HYB | Fuel Management System Hybrid v1 | Hybrid AC/DC fuel management system. | R0 | Released | 2025-12-20 00:00:00 | 2026-03-19 14:06:55

## ProductModules
LinkID | ProductCode | ModuleCode | ModuleOrder | ModuleQty | DependencyModuleCode | Notes | CreatedOn | UpdatedOn
PM::PROD-001::ASM-001 | PROD-001 | ASM-001 | 1 | 8 |  | Assembly in product structure | 2025-12-31 00:00:00 | 2026-03-17 00:00:00
PM::PROD-001::ASM-002 | PROD-001 | ASM-002 | 2 | 4 |  | Assembly in product structure | 2026-03-07 00:00:00 | 2026-03-13 00:00:00
PM::PROD-002::ASM-003 | PROD-002 | ASM-003 | 1 | 8 |  | Assembly in product structure | 2026-01-08 00:00:00 | 2026-03-12 00:00:00
PM::PROD-002::ASM-004 | PROD-002 | ASM-004 | 2 | 4 |  | Assembly in product structure | 2026-02-10 00:00:00 | 2026-03-13 00:00:00
PM::PROD-003::ASM-005 | PROD-003 | ASM-005 | 1 | 8 |  | Assembly in product structure | 2025-12-23 00:00:00 | 2026-03-15 00:00:00
PM::PROD-003::ASM-006 | PROD-003 | ASM-006 | 2 | 4 |  | Assembly in product structure | 2026-02-25 00:00:00 | 2026-03-13 00:00:00
PM::PROD-004::ASM-007 | PROD-004 | ASM-007 | 1 | 8 |  | Assembly in product structure | 2026-01-31 00:00:00 | 2026-03-13 00:00:00
PM::PROD-004::ASM-008 | PROD-004 | ASM-008 | 2 | 4 |  | Assembly in product structure | 2026-03-03 00:00:00 | 2026-03-14 00:00:00
PM::PROD-005::ASM-009 | PROD-005 | ASM-009 | 1 | 8 |  | Assembly in product structure | 2026-01-20 00:00:00 | 2026-03-16 00:00:00
PM::PROD-005::ASM-010 | PROD-005 | ASM-010 | 2 | 4 |  | Assembly in product structure | 2026-02-03 00:00:00 | 2026-03-12 00:00:00
PM::PROD-006::ASM-011 | PROD-006 | ASM-011 | 1 | 1 |  | Assembly in product structure | 2026-02-17 00:00:00 | 2026-03-18 00:00:00
PM::PROD-006::ASM-012 | PROD-006 | ASM-012 | 2 | 1 |  | Assembly in product structure | 2026-01-23 00:00:00 | 2026-03-15 00:00:00
PM::PROD-006::ASM-013 | PROD-006 | ASM-013 | 3 | 1 | ASM-012 | Assembly in product structure | 2026-01-26 00:00:00 | 2026-03-16 00:00:00
PM::PROD-006::ASM-014 | PROD-006 | ASM-014 | 4 | 1 |  | Assembly in product structure | 2026-01-09 00:00:00 | 2026-03-18 00:00:00
PM::PROD-006::ASM-015 | PROD-006 | ASM-015 | 5 | 1 |  | Assembly in product structure | 2026-02-02 00:00:00 | 2026-03-14 00:00:00
PM::PROD-007::ASM-011 | PROD-007 | ASM-011 | 1 | 1 |  | Assembly in product structure | 2026-03-02 00:00:00 | 2026-03-16 00:00:00
PM::PROD-007::ASM-012 | PROD-007 | ASM-012 | 2 | 1 |  | Assembly in product structure | 2026-01-25 00:00:00 | 2026-03-12 00:00:00
PM::PROD-007::ASM-013 | PROD-007 | ASM-013 | 3 | 1 | ASM-012 | Assembly in product structure | 2026-02-07 00:00:00 | 2026-03-16 00:00:00
PM::PROD-007::ASM-015 | PROD-007 | ASM-015 | 4 | 1 | ASM-013 | Assembly in product structure | 2025-12-24 00:00:00 | 2026-03-14 00:00:00
PM::PROD-008::ASM-016 | PROD-008 | ASM-016 | 1 | 1 |  | Assembly in product structure | 2026-01-31 00:00:00 | 2026-03-12 00:00:00
PM::PROD-008::ASM-032 | PROD-008 | ASM-032 | 2 | 1 |  | Assembly in product structure | 2026-01-24 00:00:00 | 2026-03-15 00:00:00
PM::PROD-008::ASM-031 | PROD-008 | ASM-031 | 3 | 1 |  | Assembly in product structure | 2026-02-27 00:00:00 | 2026-03-17 00:00:00
PM::PROD-008::ASM-015 | PROD-008 | ASM-015 | 4 | 1 |  | Assembly in product structure | 2026-02-01 00:00:00 | 2026-03-12 00:00:00
PM::PROD-009::ASM-017 | P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC | ASM-017 | 1 | 1 |  | Assembly in product structure | 2026-02-10 00:00:00 | 2026-03-18 12:15:00
PM::PROD-009::ASM-032 | P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC | ASM-032 | 2 | 1 |  | Assembly in product structure | 2026-02-20 00:00:00 | 2026-03-18 12:15:01
PM::PROD-009::ASM-031 | P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC | ASM-031 | 3 | 1 | ASM-032 | Assembly in product structure | 2026-02-03 00:00:00 | 2026-03-18 12:15:01
PM::PROD-009::ASM-015 | P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC | ASM-015 | 4 | 1 | ASM-031 | Assembly in product structure | 2026-02-17 00:00:00 | 2026-03-18 12:15:02
PM::PROD-010::ASM-016 | P_FMS-HYB_FUEL_MANAGEMENT_SYSTEM_HYBRID_V1 | ASM-016 | 1 | 1 |  | Assembly in product structure | 2026-01-27 00:00:00 | 2026-03-19 14:06:55
PM::PROD-010::ASM-017 | P_FMS-HYB_FUEL_MANAGEMENT_SYSTEM_HYBRID_V1 | ASM-017 | 2 | 1 |  | Assembly in product structure | 2025-12-22 00:00:00 | 2026-03-19 14:06:55
PM::PROD-010::ASM-018 | P_FMS-HYB_FUEL_MANAGEMENT_SYSTEM_HYBRID_V1 | ASM-018 | 3 | 1 | ASM-017 | Assembly in product structure | 2026-02-05 00:00:00 | 2026-03-19 14:06:55
PM::PROD-010::ASM-032 | P_FMS-HYB_FUEL_MANAGEMENT_SYSTEM_HYBRID_V1 | ASM-032 | 4 | 1 |  | Assembly in product structure | 2026-02-11 00:00:00 | 2026-03-19 14:06:55
PM::PROD-010::ASM-015 | P_FMS-HYB_FUEL_MANAGEMENT_SYSTEM_HYBRID_V1 | ASM-015 | 5 | 1 | ASM-032 | Assembly in product structure | 2026-02-12 00:00:00 | 2026-03-19 14:06:55
PM::PROD-011::ASM-019 | PROD-011 | ASM-019 | 1 | 1 |  | Assembly in product structure | 2026-01-18 00:00:00 | 2026-03-17 00:00:00
PM::PROD-011::ASM-020 | PROD-011 | ASM-020 | 2 | 1 |  | Assembly in product structure | 2026-01-14 00:00:00 | 2026-03-12 00:00:00
PM::PROD-011::ASM-022 | PROD-011 | ASM-022 | 3 | 1 | ASM-020 | Assembly in product structure | 2026-01-21 00:00:00 | 2026-03-17 00:00:00
PM::PROD-012::ASM-019 | PROD-012 | ASM-019 | 1 | 1 |  | Assembly in product structure | 2026-02-14 00:00:00 | 2026-03-13 00:00:00
PM::PROD-012::ASM-021 | PROD-012 | ASM-021 | 2 | 1 |  | Assembly in product structure | 2026-01-22 00:00:00 | 2026-03-17 00:00:00
PM::PROD-012::ASM-034 | PROD-012 | ASM-034 | 3 | 1 | ASM-021 | Assembly in product structure | 2026-02-17 00:00:00 | 2026-03-14 00:00:00
PM::PROD-012::ASM-022 | PROD-012 | ASM-022 | 4 | 1 |  | Assembly in product structure | 2026-02-15 00:00:00 | 2026-03-18 00:00:00
PM::PROD-013::ASM-023 | PROD-013 | ASM-023 | 1 | 1 |  | Assembly in product structure | 2026-01-07 00:00:00 | 2026-03-13 00:00:00
PM::PROD-013::ASM-024 | PROD-013 | ASM-024 | 2 | 1 |  | Assembly in product structure | 2026-01-04 00:00:00 | 2026-03-16 00:00:00
PM::PROD-013::ASM-035 | PROD-013 | ASM-035 | 3 | 1 |  | Assembly in product structure | 2025-12-20 00:00:00 | 2026-03-14 00:00:00
PM::PROD-013::ASM-015 | PROD-013 | ASM-015 | 4 | 1 | ASM-035 | Assembly in product structure | 2026-03-05 00:00:00 | 2026-03-14 00:00:00
PM::PROD-014::ASM-025 | PROD-014 | ASM-025 | 1 | 1 |  | Assembly in product structure | 2026-03-06 00:00:00 | 2026-03-16 00:00:00
PM::PROD-014::ASM-011 | PROD-014 | ASM-011 | 2 | 1 |  | Assembly in product structure | 2026-02-11 00:00:00 | 2026-03-12 00:00:00
PM::PROD-014::ASM-026 | PROD-014 | ASM-026 | 3 | 1 | ASM-011 | Assembly in product structure | 2026-02-28 00:00:00 | 2026-03-13 00:00:00
PM::PROD-015::ASM-033 | PROD-015 | ASM-033 | 1 | 1 |  | Assembly in product structure | 2026-02-24 00:00:00 | 2026-03-18 00:00:00
PM::PROD-015::ASM-026 | PROD-015 | ASM-026 | 2 | 1 |  | Assembly in product structure | 2026-03-05 00:00:00 | 2026-03-18 00:00:00
PM::PROD-015::ASM-032 | PROD-015 | ASM-032 | 3 | 1 |  | Assembly in product structure | 2025-12-23 00:00:00 | 2026-03-12 00:00:00
PM::PROD-016::ASM-027 | PROD-016 | ASM-027 | 1 | 1 |  | Assembly in product structure | 2026-03-04 00:00:00 | 2026-03-14 00:00:00
PM::PROD-016::ASM-014 | PROD-016 | ASM-014 | 2 | 1 |  | Assembly in product structure | 2026-01-16 00:00:00 | 2026-03-14 00:00:00
PM::PROD-017::ASM-028 | PROD-017 | ASM-028 | 1 | 1 |  | Assembly in product structure | 2026-01-20 00:00:00 | 2026-03-16 00:00:00
PM::PROD-017::ASM-011 | PROD-017 | ASM-011 | 2 | 1 |  | Assembly in product structure | 2025-12-20 00:00:00 | 2026-03-12 00:00:00
PM::PROD-017::ASM-033 | PROD-017 | ASM-033 | 3 | 1 | ASM-011 | Assembly in product structure | 2026-02-05 00:00:00 | 2026-03-13 00:00:00
PM::PROD-017::ASM-015 | PROD-017 | ASM-015 | 4 | 1 |  | Assembly in product structure | 2026-01-07 00:00:00 | 2026-03-13 00:00:00
PM::PROD-018::ASM-029 | PROD-018 | ASM-029 | 1 | 1 |  | Assembly in product structure | 2025-12-20 00:00:00 | 2026-03-14 00:00:00
PM::PROD-018::ASM-030 | PROD-018 | ASM-030 | 2 | 1 |  | Assembly in product structure | 2026-01-24 00:00:00 | 2026-03-14 00:00:00
PM::PROD-018::ASM-015 | PROD-018 | ASM-015 | 3 | 1 |  | Assembly in product structure | 2025-12-27 00:00:00 | 2026-03-12 00:00:00
PM::PROD-019::ASM-011 | PROD-019 | ASM-011 | 1 | 1 |  | Assembly in product structure | 2025-12-31 00:00:00 | 2026-03-18 00:00:00
PM::PROD-019::ASM-012 | PROD-019 | ASM-012 | 2 | 1 |  | Assembly in product structure | 2026-01-12 00:00:00 | 2026-03-14 00:00:00
PM::PROD-019::ASM-030 | PROD-019 | ASM-030 | 3 | 1 | ASM-012 | Assembly in product structure | 2026-02-27 00:00:00 | 2026-03-15 00:00:00
PM::PROD-019::ASM-014 | PROD-019 | ASM-014 | 4 | 1 | ASM-030 | Assembly in product structure | 2025-12-18 00:00:00 | 2026-03-18 00:00:00
PM::PROD-019::ASM-015 | PROD-019 | ASM-015 | 5 | 1 | ASM-014 | Assembly in product structure | 2025-12-21 00:00:00 | 2026-03-15 00:00:00
PM::PROD-020::ASM-031 | PROD-020 | ASM-031 | 1 | 1 |  | Assembly in product structure | 2026-01-14 00:00:00 | 2026-03-17 00:00:00
PM::PROD-020::ASM-015 | PROD-020 | ASM-015 | 2 | 1 |  | Assembly in product structure | 2026-02-15 00:00:00 | 2026-03-17 00:00:00

## ProductDocuments
ProdDocID | ProductCode | SectionName | DocName | DocType | FilePath | InstructionText | AddedOn | UpdatedOn
PD::PROD-001 | PROD-001 | Quote Pack | PROD-001_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-001_quote_pack.pdf | Quote pack and GA drawing | 2026-02-24 00:00:00 | 2026-03-16 00:00:00
PD::PROD-002 | PROD-002 | Quote Pack | PROD-002_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-002_quote_pack.pdf | Quote pack and GA drawing | 2026-02-18 00:00:00 | 2026-03-15 00:00:00
PD::PROD-003 | PROD-003 | Quote Pack | PROD-003_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-003_quote_pack.pdf | Quote pack and GA drawing | 2026-03-07 00:00:00 | 2026-03-17 00:00:00
PD::PROD-004 | PROD-004 | Quote Pack | PROD-004_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-004_quote_pack.pdf | Quote pack and GA drawing | 2026-03-07 00:00:00 | 2026-03-16 00:00:00
PD::PROD-005 | PROD-005 | Quote Pack | PROD-005_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-005_quote_pack.pdf | Quote pack and GA drawing | 2026-03-05 00:00:00 | 2026-03-18 00:00:00
PD::PROD-006 | PROD-006 | Quote Pack | PROD-006_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-006_quote_pack.pdf | Quote pack and GA drawing | 2026-03-11 00:00:00 | 2026-03-15 00:00:00
PD::PROD-007 | PROD-007 | Quote Pack | PROD-007_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-007_quote_pack.pdf | Quote pack and GA drawing | 2026-02-16 00:00:00 | 2026-03-18 00:00:00
PD::PROD-008 | PROD-008 | Quote Pack | PROD-008_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-008_quote_pack.pdf | Quote pack and GA drawing | 2026-02-26 00:00:00 | 2026-03-18 00:00:00
PD::PROD-009 | P_FMS-DC_FUEL_MANAGEMENT_SYSTEM_DC | Quote Pack | PROD-009_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-009_quote_pack.pdf | Quote pack and GA drawing | 2026-03-12 00:00:00 | 2026-03-18 12:15:02
PD::PROD-010 | P_FMS-HYB_FUEL_MANAGEMENT_SYSTEM_HYBRID_V1 | Quote Pack | PROD-010_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-010_quote_pack.pdf | Quote pack and GA drawing | 2026-02-18 00:00:00 | 2026-03-19 14:06:55
PD::PROD-011 | PROD-011 | Quote Pack | PROD-011_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-011_quote_pack.pdf | Quote pack and GA drawing | 2026-02-27 00:00:00 | 2026-03-16 00:00:00
PD::PROD-012 | PROD-012 | Quote Pack | PROD-012_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-012_quote_pack.pdf | Quote pack and GA drawing | 2026-02-25 00:00:00 | 2026-03-18 00:00:00
PD::PROD-013 | PROD-013 | Quote Pack | PROD-013_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-013_quote_pack.pdf | Quote pack and GA drawing | 2026-02-22 00:00:00 | 2026-03-17 00:00:00
PD::PROD-014 | PROD-014 | Quote Pack | PROD-014_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-014_quote_pack.pdf | Quote pack and GA drawing | 2026-03-12 00:00:00 | 2026-03-17 00:00:00
PD::PROD-015 | PROD-015 | Quote Pack | PROD-015_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-015_quote_pack.pdf | Quote pack and GA drawing | 2026-03-13 00:00:00 | 2026-03-16 00:00:00
PD::PROD-016 | PROD-016 | Quote Pack | PROD-016_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-016_quote_pack.pdf | Quote pack and GA drawing | 2026-02-28 00:00:00 | 2026-03-15 00:00:00
PD::PROD-017 | PROD-017 | Quote Pack | PROD-017_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-017_quote_pack.pdf | Quote pack and GA drawing | 2026-02-19 00:00:00 | 2026-03-16 00:00:00
PD::PROD-018 | PROD-018 | Quote Pack | PROD-018_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-018_quote_pack.pdf | Quote pack and GA drawing | 2026-02-27 00:00:00 | 2026-03-16 00:00:00
PD::PROD-019 | PROD-019 | Quote Pack | PROD-019_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-019_quote_pack.pdf | Quote pack and GA drawing | 2026-02-19 00:00:00 | 2026-03-15 00:00:00
PD::PROD-020 | PROD-020 | Quote Pack | PROD-020_quote_pack.pdf | PDF | C:\Liquimech\docs\products\PROD-020_quote_pack.pdf | Quote pack and GA drawing | 2026-02-18 00:00:00 | 2026-03-18 00:00:00

## Projects
ProjectCode | QuoteRef | ProjectName | ClientName | Location | Description | LinkedProductCode | Status | StartDate | DueDate | CreatedOn | UpdatedOn
ORD-001 | OQ-001 | Standpipe 2 inch Order 1 | Client 01 | Adelaide | Live order for Standpipe 2 inch | PROD-001 | Active | 2026-03-08 | 2026-03-20 | 2026-03-09 00:00:00 | 2026-03-18 00:00:00
ORD-002 | OQ-002 | Standpipe 4 inch Order 2 | Client 02 | Auckland | Live order for Standpipe 4 inch | PROD-002 | Active | 2026-03-09 | 2026-03-23 | 2026-03-12 00:00:00 | 2026-03-16 00:00:00
ORD-003 | OQ-003 | Standpipe 6 inch Order 3 | Client 03 | Adelaide | Live order for Standpipe 6 inch | PROD-003 | Active | 2026-03-15 | 2026-04-09 | 2026-03-14 00:00:00 | 2026-03-18 00:00:00
ORD-004 | OQ-004 | Standpipe 8 inch Order 4 | Client 04 | Alice Springs | Live order for Standpipe 8 inch | PROD-004 | Active | 2026-03-16 | 2026-04-10 | 2026-03-15 00:00:00 | 2026-03-17 00:00:00
ORD-005 | OQ-005 | Standpipe 10 inch Order 5 | Client 05 | Melbourne | Live order for Standpipe 10 inch | PROD-005 | Active | 2026-03-16 | 2026-03-27 | 2026-03-01 00:00:00 | 2026-03-17 00:00:00
ORD-006 | OQ-006 | Smart Water Access 12V Order 6 | Client 06 | Perth | Live order for Smart Water Access 12V | PROD-006 | Active | 2026-03-12 | 2026-03-25 | 2026-02-28 00:00:00 | 2026-03-16 00:00:00
ORD-007 | OQ-007 | Smart Water Access Solar Lite Order 7 | Client 07 | Darwin | Live order for Smart Water Access Solar Lite | PROD-007 | Active | 2026-03-11 | 2026-04-01 | 2026-02-27 00:00:00 | 2026-03-16 00:00:00
ORD-008 | OQ-008 | Fuel Management System AC Order 8 | Client 08 | Darwin | Live order for Fuel Management System AC | PROD-008 | Active | 2026-03-11 | 2026-04-04 | 2026-03-01 00:00:00 | 2026-03-16 00:00:00
PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | OQ-008 | Fuel Management System AC Order 8 | Client 08 | Darwin | Live order for Fuel Management System AC | PROD-016 | Completed | 2026-03-11 | 2026-04-04 | 2026-03-01 00:00:00 | 2026-03-19 14:50:21
PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | OQ-001 | Standpipe 2 inch Order 1 | Client 01 | Adelaide | Live order for Standpipe 2 inch | PROD-001 | Completed | 2026-03-08 | 2026-03-20 | 2026-03-09 00:00:00 | 2026-03-18 18:56:44
PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | OQ-003 | Standpipe 6 inch Order 3 | Client 03 | Adelaide | Live order for Standpipe 6 inch | PROD-003 | Completed | 2026-03-15 | 2026-04-09 | 2026-03-14 00:00:00 | 2026-03-18 19:13:37
PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | OQ-004 | Standpipe 8 inch Order 4 | Client 04 | Alice Springs | Live order for Standpipe 8 inch | PROD-004 | Completed | 2026-03-16 | 2026-04-10 | 2026-03-15 00:00:00 | 2026-03-19 08:58:22

## ProjectModules
LinkID | ProjectCode | ModuleCode | SourceType | SourceCode | ModuleOrder | ModuleQty | Stage | Status | DependencyModuleCode | Notes | CreatedOn | UpdatedOn
PRJM::ORD-001::ASM-001 | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-001 | FROM_PRODUCT | PROD-001 | 1 | 8 | Complete | Complete |  | From linked product [FINISH] 2026-03-18 18:24:32 | 2026-03-16 00:00:00 | 2026-03-18 18:24:32
PRJM::ORD-001::ASM-002 | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-002 | FROM_PRODUCT | PROD-001 | 2 | 4 | Complete | Complete |  | From linked product | 2026-03-03 00:00:00 | 2026-03-18 18:24:11
PRJM::ORD-002::ASM-003 | ORD-002 | ASM-003 | FROM_PRODUCT | PROD-002 | 1 | 8 | Fabrication | Fabrication |  | From linked product | 2026-03-11 00:00:00 | 2026-03-18 19:12:30
PRJM::ORD-002::ASM-004 | ORD-002 | ASM-004 | FROM_PRODUCT | PROD-002 | 2 | 4 | Automation | Automation |  | From linked product | 2026-03-17 00:00:00 | 2026-03-18 19:12:20
PRJM::ORD-003::ASM-005 | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-005 | FROM_PRODUCT | PROD-003 | 1 | 8 | Assembly | Not Started |  | From linked product | 2026-03-05 00:00:00 | 2026-03-18 19:13:37
PRJM::ORD-003::ASM-006 | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-006 | FROM_PRODUCT | PROD-003 | 2 | 4 | Assembly | Not Started |  | From linked product | 2026-03-04 00:00:00 | 2026-03-18 19:13:38
PRJM::ORD-004::ASM-007 | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-007 | FROM_PRODUCT | PROD-004 | 1 | 8 | Assembly | Not Started |  | From linked product | 2026-03-16 00:00:00 | 2026-03-19 08:58:23
PRJM::ORD-004::ASM-008 | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-008 | FROM_PRODUCT | PROD-004 | 2 | 4 | Assembly | Not Started |  | From linked product | 2026-03-17 00:00:00 | 2026-03-19 08:58:23
PRJM::ORD-005::ASM-009 | ORD-005 | ASM-009 | FROM_PRODUCT | PROD-005 | 1 | 8 | Not Started | Not Started |  | From linked product | 2026-03-14 00:00:00 | 2026-03-19 14:45:39
PRJM::ORD-005::ASM-010 | ORD-005 | ASM-010 | FROM_PRODUCT | PROD-005 | 2 | 4 | Assembly | Not Started |  | From linked product | 2026-03-12 00:00:00 | 2026-03-16 00:00:00
PRJM::ORD-006::ASM-011 | ORD-006 | ASM-011 | FROM_PRODUCT | PROD-006 | 1 | 1 | Assembly | Not Started |  | From linked product | 2026-03-04 00:00:00 | 2026-03-18 00:00:00
PRJM::ORD-006::ASM-012 | ORD-006 | ASM-012 | FROM_PRODUCT | PROD-006 | 2 | 1 | Assembly | Not Started |  | From linked product | 2026-02-28 00:00:00 | 2026-03-17 00:00:00
PRJM::ORD-006::ASM-013 | ORD-006 | ASM-013 | FROM_PRODUCT | PROD-006 | 3 | 1 | Assembly | Not Started | ASM-012 | From linked product | 2026-03-04 00:00:00 | 2026-03-18 00:00:00
PRJM::ORD-006::ASM-014 | ORD-006 | ASM-014 | FROM_PRODUCT | PROD-006 | 4 | 1 | Assembly | Not Started |  | From linked product | 2026-03-12 00:00:00 | 2026-03-17 00:00:00
PRJM::ORD-006::ASM-015 | ORD-006 | ASM-015 | FROM_PRODUCT | PROD-006 | 5 | 1 | Assembly | Not Started |  | From linked product | 2026-03-09 00:00:00 | 2026-03-18 00:00:00
PRJM::ORD-007::ASM-011 | ORD-007 | ASM-011 | FROM_PRODUCT | PROD-007 | 1 | 1 | Assembly | Not Started |  | From linked product | 2026-02-27 00:00:00 | 2026-03-17 00:00:00
PRJM::ORD-007::ASM-012 | ORD-007 | ASM-012 | FROM_PRODUCT | PROD-007 | 2 | 1 | Assembly | Not Started |  | From linked product | 2026-03-15 00:00:00 | 2026-03-16 00:00:00
PRJM::ORD-007::ASM-013 | ORD-007 | ASM-013 | FROM_PRODUCT | PROD-007 | 3 | 1 | Assembly | Not Started | ASM-012 | From linked product | 2026-03-13 00:00:00 | 2026-03-16 00:00:00
PRJM::ORD-007::ASM-015 | ORD-007 | ASM-015 | FROM_PRODUCT | PROD-007 | 4 | 1 | Assembly | Not Started | ASM-013 | From linked product | 2026-03-01 00:00:00 | 2026-03-16 00:00:00
PRJM::ORD-008::ASM-016 | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-016 | FROM_PRODUCT | PROD-008 | 1 | 1 | Not Started | Not Started |  | From linked product | 2026-03-13 00:00:00 | 2026-03-19 14:45:59
PRJM::ORD-008::ASM-032 | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-032 | FROM_PRODUCT | PROD-008 | 2 | 1 | Assembly | Not Started |  | From linked product | 2026-03-04 00:00:00 | 2026-03-18 18:11:35
PRJM::ORD-008::ASM-031 | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-031 | FROM_PRODUCT | PROD-008 | 3 | 1 | Assembly | Not Started |  | From linked product | 2026-03-06 00:00:00 | 2026-03-18 18:11:35
PRJM::ORD-008::ASM-015 | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-015 | FROM_PRODUCT | PROD-008 | 4 | 1 | Assembly | Not Started |  | From linked product | 2026-03-07 00:00:00 | 2026-03-18 18:11:36

## ProjectTasks
ProjectTaskID | ProjectCode | ModuleCode | SourceTaskID | ParentProjectTaskID | TaskName | Department | EstimatedHours | Stage | Status | DependencyTaskID | AssignedTo | Notes | CreatedOn | UpdatedOn
PT::ORD-001::ASM-001::Buck_weld_setup | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-001 | T::ASM-001::01 |  | Buck weld setup | Assembly | 1.6 | Complete | Complete |  | Alex | From assembly ASM-001 | 2026-02-26 00:00:00 | 2026-03-18 18:20:12
PT::ORD-001::ASM-001::Buck_weld_fit-off | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-001 | T::ASM-001::02 |  | Buck weld fit-off | Assembly | 2.4 | Complete | Complete |  | Raj | From assembly ASM-001 | 2026-03-16 00:00:00 | 2026-03-18 18:20:12
PT::ORD-001::ASM-002::Bend_prep | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-002 | T::ASM-002::01 |  | Bend prep | Assembly | 1.4 | Complete | Complete |  | Alex | From assembly ASM-002 | 2026-03-12 00:00:00 | 2026-03-18 18:24:12
PT::ORD-001::ASM-002::Bend_finish | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-002 | T::ASM-002::02 |  | Bend finish | Assembly | 1.6 | Complete | Complete |  | Raj | From assembly ASM-002 | 2026-03-02 00:00:00 | 2026-03-18 18:24:12
PT::ORD-002::ASM-003::Buck_weld_setup | ORD-002 | ASM-003 | T::ASM-003::01 |  | Buck weld setup | Fabrication | 1.6 | Fabrication | Fabrication |  | Alex | From assembly ASM-003 | 2026-03-16 00:00:00 | 2026-03-18 19:12:31
PT::ORD-002::ASM-003::Buck_weld_fit-off | ORD-002 | ASM-003 | T::ASM-003::02 |  | Buck weld fit-off | Fabrication | 2.4 | Fabrication | Fabrication |  | Raj | From assembly ASM-003 | 2026-03-06 00:00:00 | 2026-03-18 19:12:31
PT::ORD-002::ASM-004::Bend_prep | ORD-002 | ASM-004 | T::ASM-004::01 |  | Bend prep | Automation | 1.4 | Automation | Automation |  | Alex | From assembly ASM-004 | 2026-03-04 00:00:00 | 2026-03-18 19:12:20
PT::ORD-002::ASM-004::Bend_finish | ORD-002 | ASM-004 | T::ASM-004::02 |  | Bend finish | Automation | 1.6 | Automation | Automation |  | Raj | From assembly ASM-004 | 2026-03-12 00:00:00 | 2026-03-18 19:12:20
PT::ORD-003::ASM-005::Buck_weld_setup | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-005 | T::ASM-005::01 |  | Buck weld setup | Fabrication | 1.6 | Complete | Complete |  | Alex | From assembly ASM-005 | 2026-03-08 00:00:00 | 2026-03-18 19:13:38
PT::ORD-003::ASM-005::Buck_weld_fit-off | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-005 | T::ASM-005::02 |  | Buck weld fit-off | Operations/Assembly | 2.4 | Assembly | Not Started |  | Raj | From assembly ASM-005 | 2026-03-12 00:00:00 | 2026-03-18 19:13:39
PT::ORD-003::ASM-006::Bend_prep | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-006 | T::ASM-006::01 |  | Bend prep | Fabrication | 1.4 | Assembly | Not Started |  | Alex | From assembly ASM-006 | 2026-02-28 00:00:00 | 2026-03-18 19:13:39
PT::ORD-003::ASM-006::Bend_finish | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-006 | T::ASM-006::02 |  | Bend finish | Operations/Assembly | 1.6 | Assembly | Not Started |  | Raj | From assembly ASM-006 | 2026-03-10 00:00:00 | 2026-03-18 19:13:39
PT::ORD-004::ASM-007::Buck_weld_setup | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-007 | T::ASM-007::01 |  | Buck weld setup | Fabrication | 1.6 | Assembly | Not Started |  | Alex | From assembly ASM-007 | 2026-03-11 00:00:00 | 2026-03-19 08:58:23
PT::ORD-004::ASM-007::Buck_weld_fit-off | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-007 | T::ASM-007::02 |  | Buck weld fit-off | Operations/Assembly | 2.4 | Assembly | Not Started |  | Raj | From assembly ASM-007 | 2026-03-04 00:00:00 | 2026-03-19 08:58:23
PT::ORD-004::ASM-008::Bend_prep | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-008 | T::ASM-008::01 |  | Bend prep | Fabrication | 1.4 | Assembly | Not Started |  | Alex | From assembly ASM-008 | 2026-03-03 00:00:00 | 2026-03-19 08:58:23
PT::ORD-004::ASM-008::Bend_finish | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-008 | T::ASM-008::02 |  | Bend finish | Operations/Assembly | 1.6 | Assembly | Not Started |  | Raj | From assembly ASM-008 | 2026-03-14 00:00:00 | 2026-03-19 08:58:24
PT::ORD-005::ASM-009::Buck_weld_setup | ORD-005 | ASM-009 | T::ASM-009::01 |  | Buck weld setup | Procurement | 1.6 | Not Started | Not Started |  | Alex | From assembly ASM-009 | 2026-03-08 00:00:00 | 2026-03-19 14:45:39
PT::ORD-005::ASM-009::Buck_weld_fit-off | ORD-005 | ASM-009 | T::ASM-009::02 |  | Buck weld fit-off | Procurement | 2.4 | Not Started | Not Started |  | Raj | From assembly ASM-009 | 2026-03-02 00:00:00 | 2026-03-19 14:45:39
PT::ORD-005::ASM-010::Bend_prep | ORD-005 | ASM-010 | T::ASM-010::01 |  | Bend prep | Fabrication | 1.4 | Assembly | Not Started |  | Alex | From assembly ASM-010 | 2026-03-13 00:00:00 | 2026-03-16 00:00:00
PT::ORD-005::ASM-010::Bend_finish | ORD-005 | ASM-010 | T::ASM-010::02 |  | Bend finish | Operations/Assembly | 1.6 | Assembly | Not Started |  | Raj | From assembly ASM-010 | 2026-03-17 00:00:00 | 2026-03-16 00:00:00
PT::ORD-006::ASM-011::Telemetry_layout | ORD-006 | ASM-011 | T::ASM-011::01 |  | Telemetry layout | Electrical/Automation | 0.6 | Design | Not Started |  | Sachin | From assembly ASM-011 | 2026-03-09 00:00:00 | 2026-03-17 00:00:00
PT::ORD-006::ASM-011::Battery_and_solar_fitout | ORD-006 | ASM-011 | T::ASM-011::02 |  | Battery and solar fitout | Electrical/Automation | 1 | Assembly | Not Started |  | Sachin | From assembly ASM-011 | 2026-03-10 00:00:00 | 2026-03-16 00:00:00
PT::ORD-006::ASM-011::Telemetry_commissioning | ORD-006 | ASM-011 | T::ASM-011::03 |  | Telemetry commissioning | Software | 0.9 | Testing | Not Started |  | Aayush | From assembly ASM-011 | 2026-03-15 00:00:00 | 2026-03-18 00:00:00
PT::ORD-006::ASM-012::Frame_drawing_review | ORD-006 | ASM-012 | T::ASM-012::01 |  | Frame drawing review | GA Drawing/Mechanical | 0.5 | Design | Not Started |  | Ryan | From assembly ASM-012 | 2026-03-03 00:00:00 | 2026-03-17 00:00:00
PT::ORD-006::ASM-012::Frame_fabrication | ORD-006 | ASM-012 | T::ASM-012::02 |  | Frame fabrication | Fabrication | 1.8 | Assembly | Not Started |  | Alex | From assembly ASM-012 | 2026-03-16 00:00:00 | 2026-03-17 00:00:00
PT::ORD-006::ASM-012::Frame_finish | ORD-006 | ASM-012 | T::ASM-012::03 |  | Frame finish | Operations/Assembly | 0.7 | Assembly | Not Started |  | Raj | From assembly ASM-012 | 2026-03-16 00:00:00 | 2026-03-16 00:00:00
PT::ORD-006::ASM-013::Fit_frame_to_panel | ORD-006 | ASM-013 | T::ASM-013::01 |  | Fit frame to panel | Fabrication | 0.5 | Assembly | Not Started |  | Alex | From assembly ASM-013 | 2026-02-28 00:00:00 | 2026-03-18 00:00:00
PT::ORD-006::ASM-013::Panel_mounting | ORD-006 | ASM-013 | T::ASM-013::02 |  | Panel mounting | Operations/Assembly | 0.75 | Assembly | Not Started |  | Raj | From assembly ASM-013 | 2026-03-08 00:00:00 | 2026-03-18 00:00:00
PT::ORD-006::ASM-014::Panel_design | ORD-006 | ASM-014 | T::ASM-014::01 |  | Panel design | Electrical/Automation | 1 | Design | Not Started |  | Sachin | From assembly ASM-014 | 2026-02-27 00:00:00 | 2026-03-18 00:00:00
PT::ORD-006::ASM-014::Panel_build | ORD-006 | ASM-014 | T::ASM-014::02 |  | Panel build | Electrical/Automation | 2 | Assembly | Not Started |  | Sachin | From assembly ASM-014 | 2026-03-13 00:00:00 | 2026-03-18 00:00:00
PT::ORD-006::ASM-014::Panel_test | ORD-006 | ASM-014 | T::ASM-014::03 |  | Panel test | Software | 1 | Testing | Not Started |  | Aayush | From assembly ASM-014 | 2026-02-28 00:00:00 | 2026-03-17 00:00:00
PT::ORD-006::ASM-015::Mechanical_integration | ORD-006 | ASM-015 | T::ASM-015::01 |  | Mechanical integration | Operations/Assembly | 1 | Assembly | Not Started |  | Raj | From assembly ASM-015 | 2026-02-28 00:00:00 | 2026-03-18 00:00:00
PT::ORD-006::ASM-015::I/O_integration | ORD-006 | ASM-015 | T::ASM-015::02 |  | I/O integration | Electrical/Automation | 0.5 | Assembly | Not Started |  | Sachin | From assembly ASM-015 | 2026-02-27 00:00:00 | 2026-03-17 00:00:00
PT::ORD-006::ASM-015::Final_commissioning | ORD-006 | ASM-015 | T::ASM-015::03 |  | Final commissioning | Software | 0.5 | Testing | Not Started |  | Aayush | From assembly ASM-015 | 2026-03-05 00:00:00 | 2026-03-18 00:00:00
PT::ORD-007::ASM-011::Telemetry_layout | ORD-007 | ASM-011 | T::ASM-011::01 |  | Telemetry layout | Electrical/Automation | 0.6 | Design | Not Started |  | Sachin | From assembly ASM-011 | 2026-03-12 00:00:00 | 2026-03-17 00:00:00
PT::ORD-007::ASM-011::Battery_and_solar_fitout | ORD-007 | ASM-011 | T::ASM-011::02 |  | Battery and solar fitout | Electrical/Automation | 1 | Assembly | Not Started |  | Sachin | From assembly ASM-011 | 2026-03-15 00:00:00 | 2026-03-17 00:00:00
PT::ORD-007::ASM-011::Telemetry_commissioning | ORD-007 | ASM-011 | T::ASM-011::03 |  | Telemetry commissioning | Software | 0.9 | Testing | Not Started |  | Aayush | From assembly ASM-011 | 2026-03-02 00:00:00 | 2026-03-18 00:00:00
PT::ORD-007::ASM-012::Frame_drawing_review | ORD-007 | ASM-012 | T::ASM-012::01 |  | Frame drawing review | GA Drawing/Mechanical | 0.5 | Design | Not Started |  | Ryan | From assembly ASM-012 | 2026-03-10 00:00:00 | 2026-03-17 00:00:00
PT::ORD-007::ASM-012::Frame_fabrication | ORD-007 | ASM-012 | T::ASM-012::02 |  | Frame fabrication | Fabrication | 1.8 | Assembly | Not Started |  | Alex | From assembly ASM-012 | 2026-03-16 00:00:00 | 2026-03-18 00:00:00
PT::ORD-007::ASM-012::Frame_finish | ORD-007 | ASM-012 | T::ASM-012::03 |  | Frame finish | Operations/Assembly | 0.7 | Assembly | Not Started |  | Raj | From assembly ASM-012 | 2026-03-09 00:00:00 | 2026-03-18 00:00:00
PT::ORD-007::ASM-013::Fit_frame_to_panel | ORD-007 | ASM-013 | T::ASM-013::01 |  | Fit frame to panel | Fabrication | 0.5 | Assembly | Not Started |  | Alex | From assembly ASM-013 | 2026-03-08 00:00:00 | 2026-03-17 00:00:00
PT::ORD-007::ASM-013::Panel_mounting | ORD-007 | ASM-013 | T::ASM-013::02 |  | Panel mounting | Operations/Assembly | 0.75 | Assembly | Not Started |  | Raj | From assembly ASM-013 | 2026-03-16 00:00:00 | 2026-03-18 00:00:00
PT::ORD-007::ASM-015::Mechanical_integration | ORD-007 | ASM-015 | T::ASM-015::01 |  | Mechanical integration | Operations/Assembly | 1 | Assembly | Not Started |  | Raj | From assembly ASM-015 | 2026-03-04 00:00:00 | 2026-03-17 00:00:00
PT::ORD-007::ASM-015::I/O_integration | ORD-007 | ASM-015 | T::ASM-015::02 |  | I/O integration | Electrical/Automation | 0.5 | Assembly | Not Started |  | Sachin | From assembly ASM-015 | 2026-03-08 00:00:00 | 2026-03-18 00:00:00
PT::ORD-007::ASM-015::Final_commissioning | ORD-007 | ASM-015 | T::ASM-015::03 |  | Final commissioning | Software | 0.5 | Testing | Not Started |  | Aayush | From assembly ASM-015 | 2026-03-15 00:00:00 | 2026-03-17 00:00:00
PT::ORD-008::ASM-016::AC_design | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-016 | T::ASM-016::01 |  | AC design | Fabrication | 0.6 | Not Started | Not Started |  | Sachin | From assembly ASM-016 | 2026-03-08 00:00:00 | 2026-03-19 14:45:59
PT::ORD-008::ASM-016::AC_panel_build | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-016 | T::ASM-016::02 |  | AC panel build | Fabrication | 1 | Not Started | Not Started |  | Sachin | From assembly ASM-016 | 2026-03-15 00:00:00 | 2026-03-19 14:45:59
PT::ORD-008::ASM-016::AC_verification | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-016 | T::ASM-016::03 |  | AC verification | Fabrication | 0.4 | Not Started | Not Started |  | Raj | From assembly ASM-016 | 2026-03-17 00:00:00 | 2026-03-19 14:45:59
PT::ORD-008::ASM-032::Control_panel_layout | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-032 | T::ASM-032::01 |  | Control panel layout | Electrical/Automation | 1 | Design | Not Started |  | Sachin | From assembly ASM-032 | 2026-03-13 00:00:00 | 2026-03-18 18:11:38
PT::ORD-008::ASM-032::Control_panel_build | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-032 | T::ASM-032::02 |  | Control panel build | Electrical/Automation | 1.4 | Assembly | Not Started |  | Sachin | From assembly ASM-032 | 2026-03-14 00:00:00 | 2026-03-18 18:11:38
PT::ORD-008::ASM-032::PLC_commissioning | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-032 | T::ASM-032::03 |  | PLC commissioning | Software | 0.6 | Testing | Not Started |  | Aayush | From assembly ASM-032 | 2026-03-17 00:00:00 | 2026-03-18 18:11:38
PT::ORD-008::ASM-031::Panel_layout | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-031 | T::ASM-031::01 |  | Panel layout | Electrical/Automation | 0.8 | Design | Not Started |  | Sachin | From assembly ASM-031 | 2026-03-09 00:00:00 | 2026-03-18 18:11:39
PT::ORD-008::ASM-031::Panel_build | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-031 | T::ASM-031::02 |  | Panel build | Electrical/Automation | 1.4 | Assembly | Not Started |  | Sachin | From assembly ASM-031 | 2026-03-08 00:00:00 | 2026-03-18 18:11:39
PT::ORD-008::ASM-031::Panel_FAT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-031 | T::ASM-031::03 |  | Panel FAT | Operations/Assembly | 0.6 | Testing | Not Started |  | Raj | From assembly ASM-031 | 2026-03-07 00:00:00 | 2026-03-18 18:11:39
PT::ORD-008::ASM-015::Mechanical_integration | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-015 | T::ASM-015::01 |  | Mechanical integration | Operations/Assembly | 1 | Assembly | Not Started |  | Raj | From assembly ASM-015 | 2026-02-27 00:00:00 | 2026-03-18 18:11:40
PT::ORD-008::ASM-015::I/O_integration | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-015 | T::ASM-015::02 |  | I/O integration | Electrical/Automation | 0.5 | Assembly | Not Started |  | Sachin | From assembly ASM-015 | 2026-03-16 00:00:00 | 2026-03-18 18:11:40
PT::ORD-008::ASM-015::Final_commissioning | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-015 | T::ASM-015::03 |  | Final commissioning | Software | 0.5 | Testing | Not Started |  | Aayush | From assembly ASM-015 | 2026-02-27 00:00:00 | 2026-03-18 18:11:40

## ProjectDocuments
ProjectDocID | ProjectCode | SectionName | DocName | DocType | FilePath | InstructionText | AddedOn | UpdatedOn
PJD::ORD-001 | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | Order Pack | ORD-001_order_pack.pdf | PDF | C:\Liquimech\docs\orders\ORD-001_order_pack.pdf | Customer pack, QA and delivery docs | 2026-03-09 00:00:00 | 2026-03-18 18:20:14
PJD::ORD-002 | ORD-002 | Order Pack | ORD-002_order_pack.pdf | PDF | C:\Liquimech\docs\orders\ORD-002_order_pack.pdf | Customer pack, QA and delivery docs | 2026-03-04 00:00:00 | 2026-03-18 00:00:00
PJD::ORD-003 | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | Order Pack | ORD-003_order_pack.pdf | PDF | C:\Liquimech\docs\orders\ORD-003_order_pack.pdf | Customer pack, QA and delivery docs | 2026-03-13 00:00:00 | 2026-03-18 19:13:40
PJD::ORD-004 | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | Order Pack | ORD-004_order_pack.pdf | PDF | C:\Liquimech\docs\orders\ORD-004_order_pack.pdf | Customer pack, QA and delivery docs | 2026-03-17 00:00:00 | 2026-03-19 08:58:24
PJD::ORD-005 | ORD-005 | Order Pack | ORD-005_order_pack.pdf | PDF | C:\Liquimech\docs\orders\ORD-005_order_pack.pdf | Customer pack, QA and delivery docs | 2026-03-10 00:00:00 | 2026-03-16 00:00:00
PJD::ORD-006 | ORD-006 | Order Pack | ORD-006_order_pack.pdf | PDF | C:\Liquimech\docs\orders\ORD-006_order_pack.pdf | Customer pack, QA and delivery docs | 2026-03-03 00:00:00 | 2026-03-16 00:00:00
PJD::ORD-007 | ORD-007 | Order Pack | ORD-007_order_pack.pdf | PDF | C:\Liquimech\docs\orders\ORD-007_order_pack.pdf | Customer pack, QA and delivery docs | 2026-03-02 00:00:00 | 2026-03-18 00:00:00
PJD::ORD-008 | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | Order Pack | ORD-008_order_pack.pdf | PDF | C:\Liquimech\docs\orders\ORD-008_order_pack.pdf | Customer pack, QA and delivery docs | 2026-03-03 00:00:00 | 2026-03-18 18:11:41

## WorkOrders
WorkOrderID | OwnerType | OwnerCode | WorkOrderName | Stage | Owner | DueDate | Status | Notes | CreatedOn | UpdatedOn
WO::ORD-001::ASM-001::FAB | PROJECT | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-001 ¦ Fabrication | Procurement | Alex | 2026-03-10 | Completed | AUTO_TRACKER ¦ MODULE=ASM-001 ¦ QTY=Assembly in product structure | 2026-03-02 00:00:00 | 2026-03-18 18:20:14
WO::ORD-001::ASM-001::OPE | PROJECT | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-001 ¦ Operations/Assembly | Complete | Raj | 2026-03-11 | Complete | AUTO_TRACKER ¦ MODULE=ASM-001 ¦ QTY=Assembly in product structure | 2026-03-06 00:00:00 | 2026-03-18 18:24:21
WO::ORD-001::ASM-002::FAB | PROJECT | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-002 ¦ Fabrication | Complete | Alex | 2026-03-13 | Complete | AUTO_TRACKER ¦ MODULE=ASM-002 ¦ QTY=Assembly in product structure | 2026-03-09 00:00:00 | 2026-03-18 18:24:15
WO::ORD-001::ASM-002::OPE | PROJECT | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | ASM-002 ¦ Operations/Assembly | Complete | Raj | 2026-03-14 | Complete | AUTO_TRACKER ¦ MODULE=ASM-002 ¦ QTY=Assembly in product structure | 2026-03-16 00:00:00 | 2026-03-18 18:24:18
WO::ORD-002::ASM-003::FAB | PROJECT | ORD-002 | ASM-003 ¦ Fabrication | Not Started | Alex | 2026-03-11 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-003 ¦ QTY=Assembly in product structure | 2026-03-16 00:00:00 | 2026-03-19 14:46:16
WO::ORD-002::ASM-003::OPE | PROJECT | ORD-002 | ASM-003 ¦ Operations/Assembly | Not Started | Raj | 2026-03-12 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-003 ¦ QTY=Assembly in product structure | 2026-03-10 00:00:00 | 2026-03-19 14:44:21
WO::ORD-002::ASM-004::FAB | PROJECT | ORD-002 | ASM-004 ¦ Fabrication | Not Started | Alex | 2026-03-14 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-004 ¦ QTY=Assembly in product structure | 2026-03-14 00:00:00 | 2026-03-19 14:44:22
WO::ORD-002::ASM-004::OPE | PROJECT | ORD-002 | ASM-004 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-15 | Open | AUTO_TRACKER ¦ MODULE=ASM-004 ¦ QTY=Assembly in product structure | 2026-02-27 00:00:00 | 2026-03-17 00:00:00
WO::ORD-003::ASM-005::FAB | PROJECT | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-005 ¦ Fabrication | Not Started | Alex | 2026-03-17 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-005 ¦ QTY=Assembly in product structure | 2026-02-28 00:00:00 | 2026-03-19 14:06:00
WO::ORD-003::ASM-005::OPE | PROJECT | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-005 ¦ Operations/Assembly | Not Started | Raj | 2026-03-18 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-005 ¦ QTY=Assembly in product structure | 2026-03-15 00:00:00 | 2026-03-19 14:06:02
WO::ORD-003::ASM-006::FAB | PROJECT | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-006 ¦ Fabrication | Automation | Alex | 2026-03-20 | Automation | AUTO_TRACKER ¦ MODULE=ASM-006 ¦ QTY=Assembly in product structure | 2026-03-04 00:00:00 | 2026-03-18 19:13:40
WO::ORD-003::ASM-006::OPE | PROJECT | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | ASM-006 ¦ Operations/Assembly | Electrical | Raj | 2026-03-21 | Electrical | AUTO_TRACKER ¦ MODULE=ASM-006 ¦ QTY=Assembly in product structure | 2026-03-01 00:00:00 | 2026-03-18 19:13:41
WO::ORD-004::ASM-007::FAB | PROJECT | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-007 ¦ Fabrication | Not Started | Alex | 2026-03-18 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-007 ¦ QTY=Assembly in product structure | 2026-03-05 00:00:00 | 2026-03-19 14:42:17
WO::ORD-004::ASM-007::OPE | PROJECT | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-007 ¦ Operations/Assembly | Not Started | Raj | 2026-03-19 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-007 ¦ QTY=Assembly in product structure | 2026-03-13 00:00:00 | 2026-03-19 14:42:16
WO::ORD-004::ASM-008::FAB | PROJECT | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-008 ¦ Fabrication | Not Started | Alex | 2026-03-21 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-008 ¦ QTY=Assembly in product structure | 2026-03-12 00:00:00 | 2026-03-19 14:42:14
WO::ORD-004::ASM-008::OPE | PROJECT | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | ASM-008 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-22 | Open | AUTO_TRACKER ¦ MODULE=ASM-008 ¦ QTY=Assembly in product structure | 2026-02-28 00:00:00 | 2026-03-19 08:58:25
WO::ORD-005::ASM-009::FAB | PROJECT | ORD-005 | ASM-009 ¦ Fabrication | Automation | Alex | 2026-03-18 | Automation | AUTO_TRACKER ¦ MODULE=ASM-009 ¦ QTY=Assembly in product structure | 2026-03-05 00:00:00 | 2026-03-18 12:00:31
WO::ORD-005::ASM-009::OPE | PROJECT | ORD-005 | ASM-009 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-19 | Open | AUTO_TRACKER ¦ MODULE=ASM-009 ¦ QTY=Assembly in product structure | 2026-03-16 00:00:00 | 2026-03-18 00:00:00
WO::ORD-005::ASM-010::FAB | PROJECT | ORD-005 | ASM-010 ¦ Fabrication | Procurement | Alex | 2026-03-21 | Procurement | AUTO_TRACKER ¦ MODULE=ASM-010 ¦ QTY=Assembly in product structure | 2026-03-02 00:00:00 | 2026-03-18 12:00:37
WO::ORD-005::ASM-010::OPE | PROJECT | ORD-005 | ASM-010 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-22 | Open | AUTO_TRACKER ¦ MODULE=ASM-010 ¦ QTY=Assembly in product structure | 2026-02-28 00:00:00 | 2026-03-17 00:00:00
WO::ORD-006::ASM-011::ELE | PROJECT | ORD-006 | ASM-011 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-13 | Open | AUTO_TRACKER ¦ MODULE=ASM-011 ¦ QTY=Assembly in product structure | 2026-03-11 00:00:00 | 2026-03-16 00:00:00
WO::ORD-006::ASM-011::ELE | PROJECT | ORD-006 | ASM-011 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-14 | Open | AUTO_TRACKER ¦ MODULE=ASM-011 ¦ QTY=Assembly in product structure | 2026-03-09 00:00:00 | 2026-03-18 00:00:00
WO::ORD-006::ASM-011::SOF | PROJECT | ORD-006 | ASM-011 ¦ Software | Software | Aayush | 2026-03-16 | Open | AUTO_TRACKER ¦ MODULE=ASM-011 ¦ QTY=Assembly in product structure | 2026-03-04 00:00:00 | 2026-03-18 00:00:00
WO::ORD-006::ASM-012::GA | PROJECT | ORD-006 | ASM-012 ¦ GA Drawing/Mechanical | GA Drawing/Mechanical | Ryan | 2026-03-17 | Open | AUTO_TRACKER ¦ MODULE=ASM-012 ¦ QTY=Assembly in product structure | 2026-03-14 00:00:00 | 2026-03-18 00:00:00
WO::ORD-006::ASM-012::FAB | PROJECT | ORD-006 | ASM-012 ¦ Fabrication | Fabrication | Alex | 2026-03-19 | Open | AUTO_TRACKER ¦ MODULE=ASM-012 ¦ QTY=Assembly in product structure | 2026-03-12 00:00:00 | 2026-03-16 00:00:00
WO::ORD-006::ASM-012::OPE | PROJECT | ORD-006 | ASM-012 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-20 | Open | AUTO_TRACKER ¦ MODULE=ASM-012 ¦ QTY=Assembly in product structure | 2026-03-17 00:00:00 | 2026-03-16 00:00:00
WO::ORD-006::ASM-013::FAB | PROJECT | ORD-006 | ASM-013 ¦ Fabrication | Fabrication | Alex | 2026-03-22 | Open | AUTO_TRACKER ¦ MODULE=ASM-013 ¦ QTY=Assembly in product structure | 2026-03-06 00:00:00 | 2026-03-16 00:00:00
WO::ORD-006::ASM-013::OPE | PROJECT | ORD-006 | ASM-013 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-23 | Open | AUTO_TRACKER ¦ MODULE=ASM-013 ¦ QTY=Assembly in product structure | 2026-03-10 00:00:00 | 2026-03-16 00:00:00
WO::ORD-006::ASM-014::ELE | PROJECT | ORD-006 | ASM-014 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-24 | Open | AUTO_TRACKER ¦ MODULE=ASM-014 ¦ QTY=Assembly in product structure | 2026-03-09 00:00:00 | 2026-03-16 00:00:00
WO::ORD-006::ASM-014::ELE | PROJECT | ORD-006 | ASM-014 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-25 | Open | AUTO_TRACKER ¦ MODULE=ASM-014 ¦ QTY=Assembly in product structure | 2026-03-10 00:00:00 | 2026-03-16 00:00:00
WO::ORD-006::ASM-014::SOF | PROJECT | ORD-006 | ASM-014 ¦ Software | Software | Aayush | 2026-03-27 | Open | AUTO_TRACKER ¦ MODULE=ASM-014 ¦ QTY=Assembly in product structure | 2026-02-27 00:00:00 | 2026-03-17 00:00:00
WO::ORD-006::ASM-015::OPE | PROJECT | ORD-006 | ASM-015 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-28 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-01 00:00:00 | 2026-03-16 00:00:00
WO::ORD-006::ASM-015::ELE | PROJECT | ORD-006 | ASM-015 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-29 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-16 00:00:00 | 2026-03-17 00:00:00
WO::ORD-006::ASM-015::SOF | PROJECT | ORD-006 | ASM-015 ¦ Software | Software | Aayush | 2026-03-31 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-14 00:00:00 | 2026-03-17 00:00:00
WO::ORD-007::ASM-011::ELE | PROJECT | ORD-007 | ASM-011 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-12 | Open | AUTO_TRACKER ¦ MODULE=ASM-011 ¦ QTY=Assembly in product structure | 2026-03-10 00:00:00 | 2026-03-16 00:00:00
WO::ORD-007::ASM-011::ELE | PROJECT | ORD-007 | ASM-011 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-13 | Open | AUTO_TRACKER ¦ MODULE=ASM-011 ¦ QTY=Assembly in product structure | 2026-03-17 00:00:00 | 2026-03-18 00:00:00
WO::ORD-007::ASM-011::SOF | PROJECT | ORD-007 | ASM-011 ¦ Software | Software | Aayush | 2026-03-15 | Open | AUTO_TRACKER ¦ MODULE=ASM-011 ¦ QTY=Assembly in product structure | 2026-03-01 00:00:00 | 2026-03-17 00:00:00
WO::ORD-007::ASM-012::GA | PROJECT | ORD-007 | ASM-012 ¦ GA Drawing/Mechanical | GA Drawing/Mechanical | Ryan | 2026-03-16 | Open | AUTO_TRACKER ¦ MODULE=ASM-012 ¦ QTY=Assembly in product structure | 2026-03-03 00:00:00 | 2026-03-17 00:00:00
WO::ORD-007::ASM-012::FAB | PROJECT | ORD-007 | ASM-012 ¦ Fabrication | Fabrication | Alex | 2026-03-18 | Open | AUTO_TRACKER ¦ MODULE=ASM-012 ¦ QTY=Assembly in product structure | 2026-03-15 00:00:00 | 2026-03-18 00:00:00
WO::ORD-007::ASM-012::OPE | PROJECT | ORD-007 | ASM-012 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-19 | Open | AUTO_TRACKER ¦ MODULE=ASM-012 ¦ QTY=Assembly in product structure | 2026-02-28 00:00:00 | 2026-03-16 00:00:00
WO::ORD-007::ASM-013::FAB | PROJECT | ORD-007 | ASM-013 ¦ Fabrication | Fabrication | Alex | 2026-03-21 | Open | AUTO_TRACKER ¦ MODULE=ASM-013 ¦ QTY=Assembly in product structure | 2026-03-01 00:00:00 | 2026-03-17 00:00:00
WO::ORD-007::ASM-013::OPE | PROJECT | ORD-007 | ASM-013 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-22 | Open | AUTO_TRACKER ¦ MODULE=ASM-013 ¦ QTY=Assembly in product structure | 2026-02-27 00:00:00 | 2026-03-17 00:00:00
WO::ORD-007::ASM-015::OPE | PROJECT | ORD-007 | ASM-015 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-23 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-08 00:00:00 | 2026-03-18 00:00:00
WO::ORD-007::ASM-015::ELE | PROJECT | ORD-007 | ASM-015 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-24 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-06 00:00:00 | 2026-03-18 00:00:00
WO::ORD-007::ASM-015::SOF | PROJECT | ORD-007 | ASM-015 ¦ Software | Software | Aayush | 2026-03-26 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-14 00:00:00 | 2026-03-16 00:00:00
WO::ORD-008::ASM-016::ELE | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-016 ¦ Electrical/Automation | Not Started | Sachin | 2026-03-12 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-016 ¦ QTY=Assembly in product structure | 2026-03-04 00:00:00 | 2026-03-19 08:57:55
WO::ORD-008::ASM-016::ELE | PROJECT | ORD-008 | ASM-016 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-13 | Open | AUTO_TRACKER ¦ MODULE=ASM-016 ¦ QTY=Assembly in product structure | 2026-03-07 00:00:00 | 2026-03-16 00:00:00
WO::ORD-008::ASM-016::OPE | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-016 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-14 | Open | AUTO_TRACKER ¦ MODULE=ASM-016 ¦ QTY=Assembly in product structure | 2026-03-08 00:00:00 | 2026-03-18 18:11:42
WO::ORD-008::ASM-032::ELE | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-032 ¦ Electrical/Automation | Not Started | Sachin | 2026-03-15 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-032 ¦ QTY=Assembly in product structure | 2026-03-17 00:00:00 | 2026-03-19 08:57:58
WO::ORD-008::ASM-032::ELE | PROJECT | ORD-008 | ASM-032 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-16 | Open | AUTO_TRACKER ¦ MODULE=ASM-032 ¦ QTY=Assembly in product structure | 2026-02-27 00:00:00 | 2026-03-18 00:00:00
WO::ORD-008::ASM-032::SOF | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-032 ¦ Software | Software | Aayush | 2026-03-18 | Open | AUTO_TRACKER ¦ MODULE=ASM-032 ¦ QTY=Assembly in product structure | 2026-03-14 00:00:00 | 2026-03-18 18:11:43
WO::ORD-008::ASM-031::ELE | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-031 ¦ Electrical/Automation | Not Started | Sachin | 2026-03-19 | Not Started | AUTO_TRACKER ¦ MODULE=ASM-031 ¦ QTY=Assembly in product structure | 2026-03-14 00:00:00 | 2026-03-19 08:57:53
WO::ORD-008::ASM-031::ELE | PROJECT | ORD-008 | ASM-031 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-20 | Open | AUTO_TRACKER ¦ MODULE=ASM-031 ¦ QTY=Assembly in product structure | 2026-02-27 00:00:00 | 2026-03-16 00:00:00
WO::ORD-008::ASM-031::OPE | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-031 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-21 | Open | AUTO_TRACKER ¦ MODULE=ASM-031 ¦ QTY=Assembly in product structure | 2026-03-13 00:00:00 | 2026-03-18 18:11:44
WO::ORD-008::ASM-015::OPE | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-015 ¦ Operations/Assembly | Operations/Assembly | Raj | 2026-03-22 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-03 00:00:00 | 2026-03-18 18:11:44
WO::ORD-008::ASM-015::ELE | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-015 ¦ Electrical/Automation | Electrical/Automation | Sachin | 2026-03-23 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-12 00:00:00 | 2026-03-18 18:11:44
WO::ORD-008::ASM-015::SOF | PROJECT | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | ASM-015 ¦ Software | Software | Aayush | 2026-03-25 | Open | AUTO_TRACKER ¦ MODULE=ASM-015 ¦ QTY=Assembly in product structure | 2026-03-07 00:00:00 | 2026-03-18 18:11:45

## README
Note | This workbook matches the current app sheet names and headers.
Source | Generated from Liquimech_ERP_Custom_Product_Template.xlsx with app-compatible headers.
Products | 20
Modules | 35
Projects | 8

## Parts
PartID | PartNumber | PartName | Description | UnitPrice | LeadTimeDays | PreferredSupplier | StockOnHand | Manufacturer | Category | Notes | CreatedOn | UpdatedOn

## CompletedJobs
SnapshotID | ProjectCode | QuoteRef | ProductCode | ProductName | ClientName | CompletedOn | LabourHours | PartsTotal | GrandTotal | Notes
SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418 | PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8 | OQ-008 | PROD-016 | Steel Frame Kiosk | Client 08 | 2026-03-19 14:54:18 | 9.8 | 0 | 0 | Frozen snapshot created on completion.
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4 | OQ-004 | PROD-004 | Standpipe 8 inch | Client 04 | 2026-03-19 14:54:19 | 7 | 0 | 0 | Frozen snapshot created on completion.
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3 | OQ-003 | PROD-003 | Standpipe 6 inch | Client 03 | 2026-03-19 14:54:20 | 7 | 0 | 0 | Frozen snapshot created on completion.
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1 | OQ-001 | PROD-001 | Standpipe 2 inch | Client 01 | 2026-03-19 14:54:20 | 7 | 0 | 0 | Frozen snapshot created on completion.

## CompletedJobLines
SnapshotLineID | SnapshotID | LineType | Code | Description | PartNumber | Qty | Hours | UnitPrice | LineTotal | Source
SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418-ASM-001 | SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418 | ASSEMBLY | ASM-027 | ASM-027 |  | 1 | 2.8 | 0 | 0 | PRODUCT_MODULE
SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418-ASM-002 | SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418 | ASSEMBLY | ASM-014 | ASM-014 |  | 1 | 4 | 0 | 0 | PRODUCT_MODULE
SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418-PART-003 | SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418 | PART | Control Panel Door | Control Panel Door | 2026-01-08 00:00:00 | 1 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418-PART-004 | SNAP::PRJ_OQ-008_FUEL_MANAGEMENT_SYSTEM_AC_ORDER_8::20260319145418 | PART | Panel Cooling Fan | Panel Cooling Fan | 2026-01-04 00:00:00 | 1 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419-ASM-001 | SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | ASSEMBLY | ASM-007 | ASM-007 |  | 8 | 4 | 0 | 0 | PRODUCT_MODULE
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419-ASM-002 | SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | ASSEMBLY | ASM-008 | ASM-008 |  | 4 | 3 | 0 | 0 | PRODUCT_MODULE
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419-PART-003 | SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | PART | Pipe 8 inch 6 meters | Pipe 8 inch 6 meters | 2026-01-28 00:00:00 | 1 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419-PART-004 | SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | PART | Stub 8 inch | Stub 8 inch | 2026-03-08 00:00:00 | 2 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419-PART-005 | SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | PART | Poly Hinge | Poly Hinge | 2026-01-13 00:00:00 | 2 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419-PART-006 | SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | PART | Bolt M12 Galv | Bolt M12 Galv | 2026-01-31 00:00:00 | 10 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419-PART-007 | SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | PART | Lug 12mm | Lug 12mm | 2026-01-11 00:00:00 | 6 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419-PART-008 | SNAP::PRJ_OQ-004_STANDPIPE_8_INCH_ORDER_4::20260319145419 | PART | Flange 8 inch | Flange 8 inch | 2025-12-24 00:00:00 | 6 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-ASM-001 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | ASSEMBLY | ASM-005 | ASM-005 |  | 8 | 4 | 0 | 0 | PRODUCT_MODULE
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-ASM-002 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | ASSEMBLY | ASM-006 | ASM-006 |  | 4 | 3 | 0 | 0 | PRODUCT_MODULE
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-PART-003 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | PART | Pipe 6 inch 6 meters | Pipe 6 inch 6 meters | 2026-01-14 00:00:00 | 1 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-PART-004 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | PART | Stub 6 inch | Stub 6 inch | 2026-01-05 00:00:00 | 2 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-PART-005 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | PART | Poly Hinge | Poly Hinge | 2026-02-03 00:00:00 | 2 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-PART-006 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | PART | Bolt M12 Galv | Bolt M12 Galv | 2026-02-14 00:00:00 | 10 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-PART-007 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | PART | Lug 12mm | Lug 12mm | 2026-02-02 00:00:00 | 6 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-PART-008 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | PART | Flange 6 inch | Flange 6 inch | 2026-01-11 00:00:00 | 6 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420-PART-009 | SNAP::PRJ_OQ-003_STANDPIPE_6_INCH_ORDER_3::20260319145420 | PART | AC Contactor | AC Contactor | 2026-02-07 00:00:00 | 1 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420-ASM-001 | SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | ASSEMBLY | ASM-001 | ASM-001 |  | 8 | 4 | 0 | 0 | PRODUCT_MODULE
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420-ASM-002 | SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | ASSEMBLY | ASM-002 | ASM-002 |  | 4 | 3 | 0 | 0 | PRODUCT_MODULE
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420-PART-003 | SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | PART | Pipe 2 inch 6 meters | Pipe 2 inch 6 meters | 2025-12-18 00:00:00 | 1 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420-PART-004 | SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | PART | Stub 2 inch | Stub 2 inch | 2026-02-17 00:00:00 | 2 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420-PART-005 | SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | PART | Poly Hinge | Poly Hinge | 2026-01-15 00:00:00 | 2 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420-PART-006 | SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | PART | Bolt M12 Galv | Bolt M12 Galv | 2026-01-03 00:00:00 | 10 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420-PART-007 | SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | PART | Lug 12mm | Lug 12mm | 2026-03-05 00:00:00 | 6 | 0 | 0 | 0 | PRODUCT_DIRECT_PART
SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420-PART-008 | SNAP::PRJ_OQ-001_STANDPIPE_2_INCH_ORDER_1::20260319145420 | PART | Flange 2 inch | Flange 2 inch | 2025-12-19 00:00:00 | 6 | 0 | 0 | 0 | PRODUCT_DIRECT_PART